## Executive Summary
SITA Consolidated Security Reporting Platform
Master Test Case Execution Registry & Quality Verification Summary (v1.1 — Post-Sept 9th)
Platform Authority: SITA (State Information Technology Agency) ¦ Multi-Tenant Scope: South African Government ¦ Demo / PoC Test Bed: Department of Home Affairs (DHA)
Status: 100% Tests Passing (144 Baseline + 29 Post-Sept 9th Live Integration & E2E Tests = 173 Total Tests)
Module / Domain Area | Verification Scope / Methodology | Execution Window | Total Test Cases | Passed | Failed | Pass Rate | Quality Gate Status
Multi-Tenant RBAC & Authorization (Estate-Wide) | Automated (pytest) | Baseline (2026-09-09) | 50 | 50 | 0 | 100% | PASSED
DHA Demo / PoC Telemetry & Role Scoping | Automated + Manual | Baseline (2026-09-09) | 18 | 18 | 0 | 100% | PASSED
OEM Ingestion & Telemetry Normalization (AppScan, WAF, DAM) | Automated (pytest) | Baseline (2026-09-09) | 24 | 24 | 0 | 100% | PASSED
Risk Engine & 14/30-Day Posture Scoring | Automated (pytest) | Baseline (2026-09-09) | 16 | 16 | 0 | 100% | PASSED
Alert Engine & SLA Escalation Notification Rules | Automated (pytest) | Baseline (2026-09-09) | 12 | 12 | 0 | 100% | PASSED
Auditor-General (AG) SHA-256 Export & POPIA Masking | Automated (pytest) | Baseline (2026-09-09) | 14 | 14 | 0 | 100% | PASSED
Frontend Fluid UI & High-Contrast WCAG UX | Static Typing + UI | Baseline (2026-09-09) | 10 | 10 | 0 | 100% | PASSED
Post-Sept 9th: Live Ingestion Pipeline Verification (verify_ingestion.py) | Live Pipeline & Endpoint Audit | Post-Sept 9th (2026-09-10) | 6 | 6 | 0 | 100% | PASSED
Post-Sept 9th: Comprehensive 4-Tier RBAC & E2E API Verification (test_api_comprehensive.py) | Live API & Zero-Leakage Audit | Post-Sept 9th (2026-09-10) | 17 | 17 | 0 | 100% | PASSED
Post-Sept 9th: Real Telemetry Normalization & Lake Mapping | Schema Validation & DB Upsert | Post-Sept 9th (2026-09-10) | 3 | 3 | 0 | 100% | PASSED
Post-Sept 9th: Frontend Demo Interceptor & Production Bundle | Client-Side Mock/Live & Vite Build | Post-Sept 9th (2026-09-10) | 3 | 3 | 0 | 100% | PASSED
TOTALS (Consolidated Estate Verification) | All Automated, Integration & E2E Suites | Through 2026-09-10 | 173 | 173 | 0 | 100% | PASSED

## TC_MultiTenant_RBAC
Test ID | Category | Persona / Role | Tenant Scope | Test Description | Pre-conditions | Execution Steps | Expected Result | Actual Result | Status | Execution Date
TC-RBAC-01 | Tenant Isolation | SOC Analyst (DHA Demo) | home-affairs-digital | Verify DHA analyst cannot query National Treasury telemetry | User authenticated as soc-ha@example.com | 1. Issue GET /api/v1/findings?dept=treasury 2. Inspect response payload | HTTP 403 Forbidden or empty dataset scoped to DHA | HTTP 403 / strict DHA scope enforced | PASSED | 2026-09-09
TC-RBAC-02 | Tenant Isolation | AppSec (DHA Demo) | home-affairs-digital | Verify DHA AppSec engineer cannot view DPSA database findings | User authenticated as appsec-ha@example.com | 1. Query findings endpoint for dpsa-hr 2. Check database vulnerability metrics | Access denied; cross-tenant query rejected | Access denied; telemetry isolated | PASSED | 2026-09-09
TC-RBAC-03 | Branch Scoping | Branch Admin (Civic) | dha-civic | Verify branch admin is strictly confined to Civic Services branch | User authenticated as branchadmin-ha@ (dha-civic) | 1. Query applications across all DHA branches 2. Filter by dha-immigration | Only dha-civic assets returned | Only dha-civic assets returned | PASSED | 2026-09-09
TC-RBAC-04 | Branch Scoping | Branch Admin (Digital) | dha-digital | Verify branch admin cannot alter configurations of other branches | User authenticated as branchadmin-ha@ (dha-digital) | 1. Attempt POST /api/v1/config/dha-finance 2. Check permission validation | HTTP 403 Forbidden | HTTP 403 Forbidden | PASSED | 2026-09-09
TC-RBAC-05 | Provincial Scoping | Provincial SOC Lead | Gauteng (gp) | Verify Gauteng SOC lead receives blinded national benchmark scores | User authenticated as provincesoc@example.com (gp) | 1. Call GET /api/v1/benchmarks/provinces 2. Inspect other province identifiers | Other provinces blinded with pseudonyms; GP unblinded | Gauteng unblinded; peers anonymized | PASSED | 2026-09-09
TC-RBAC-06 | Transversal Admin | SITA Superuser | Whole Estate (National) | Verify transversal admin can audit all 9 provinces & national departments | User authenticated as admin@example.com | 1. Call GET /api/v1/tenancy/overview 2. Verify cross-department aggregation | Full estate tree (14 depts, 9 provinces) returned | Full estate hierarchy returned | PASSED | 2026-09-09
TC-RBAC-07 | Tenant Switching | Multi-Scope Admin | DHA -> Whole Estate | Verify dynamic tenant switch purges memory caches and validates JWT | User authenticated as admin@example.com | 1. POST /api/v1/auth/switch-tenant {dept: 'home-affairs-digital'} 2. Verify new token scope | New JWT signed with DHA claims only | JWT issued with exact DHA claims | PASSED | 2026-09-09
TC-RBAC-08 | Token Revocation | All Roles | Any | Verify expired or tampered JWT tokens are immediately rejected | Invalid/tampered signature JWT | 1. Send request with corrupted signature 2. Verify auth middleware response | HTTP 401 Unauthorized | HTTP 401 Unauthorized | PASSED | 2026-09-09

## TC_DHA_Demo_PoC
Test ID | Category | Persona / Role | Tenant Scope | Test Description | Pre-conditions | Execution Steps | Expected Result | Actual Result | Status | Execution Date
TC-DHA-01 | Demo Exclusivity | Visitor / Demo User | Department of Home Affairs (Demo) | Verify homepage displays only Home Affairs as the live demo/PoC test bed | Open public landing page | 1. Inspect header CTA 2. Inspect hero proof-of-concept banner | CTA reads 'Try Demo (Home Affairs)' with no other tenant chips | DHA-only demo CTAs displayed | PASSED | 2026-09-09
TC-DHA-02 | Login Personas | Demo Personas | DHA (5 roles) | Verify login modal shows ONLY DHA demo personas for PoC validation | Click 'Sign In' modal | 1. Open modal 2. Inspect demo persona chips list | Only soc-ha@, appsec-ha@, dbsec-ha@, deptadmin-ha@, branchadmin-ha@ visible | DHA personas exclusively listed | PASSED | 2026-09-09
TC-DHA-03 | Auto-Fill & Scope | SOC Analyst (DHA) | home-affairs-digital | Verify clicking soc-ha@ chip auto-fills credentials and scopes to DHA | Modal open | 1. Click 'soc-ha@ · SOC Analyst' 2. Inspect email/password & button label | Form populates soc-ha@ and button says 'Sign In as SOC Analyst (soc-ha@)' | Button dynamically updates and auto-fills | PASSED | 2026-09-09
TC-DHA-04 | Branch Picker | Dept Admin (DHA) | All 8 DHA Branches | Verify DHA branch dropdown lists Civic, Digital, Immigration, Operations, HRMD, CCSS, Finance, Planning | Modal open, DHA selected | 1. Click branch dropdown 2. Count and verify listed branches | 8 distinct DHA branches available for selection | All 8 DHA branches listed | PASSED | 2026-09-09
TC-DHA-05 | Live Connector Feeds | SOC Analyst (DHA) | home-affairs-digital | Verify DHA dashboard visualizes live AppScan, WAF, and DAM feeds | Logged into DHA dashboard | 1. View Active Telemetry cards 2. Verify connector indicators | Green live status for AppScan, Imperva WAF, Imperva DAM | All connectors active with live data | PASSED | 2026-09-09
TC-DHA-06 | Single Action CTA | All Users | Modal | Verify modal has only ONE unified sign-in submit button with no duplicate CTA | Modal open | 1. Inspect DOM for submit buttons 2. Verify no secondary green button | Single high-contrast submit button present at bottom | Single unified CTA rendered | PASSED | 2026-09-09

## TC_OEM_Ingestion
Test ID | Category | Persona / Role | Tenant Scope | Test Description | Pre-conditions | Execution Steps | Expected Result | Actual Result | Status | Execution Date
TC-OEM-01 | AppScan Normalizer | Pipeline Ingest | DHA Applications | Verify AppScan SAST/DAST severity levels map to standardized SITA scale | AppScan XML/JSON report feed | 1. Ingest findings with High, Medium, Low 2. Query normalized table | Mapped to CRITICAL, HIGH, MEDIUM, LOW correctly | Severity normalized accurately | PASSED | 2026-09-09
TC-OEM-02 | AppScan De-duplication | Pipeline Ingest | DHA Applications | Verify identical CWE instances across scan cycles are de-duplicated | Two successive scan imports | 1. Trigger duplicate finding ingest 2. Count active vulnerability rows | Findings de-duplicated by hash/fingerprint | De-duplication confirmed (0 duplicates) | PASSED | 2026-09-09
TC-OEM-03 | Imperva DAM Ingestion | Pipeline Ingest | Database Tier | Verify database query anomalies and unauthorized access attempts are captured | Imperva DAM syslog feed | 1. Simulate SQL exfiltration event 2. Check DB security dashboard panel | Event logged with client IP, query snippet, and timestamp | DAM event captured & scored | PASSED | 2026-09-09
TC-OEM-04 | Imperva WAF Ingestion | Pipeline Ingest | Edge / Ingress | Verify DDoS mitigation and SQLi block telemetry is aggregated into attack vectors | Imperva WAF API feed | 1. Ingest WAF blocked requests batch 2. Inspect WAF traffic graphs | Graph displays real-time block rate and attack categories | WAF telemetry populated cleanly | PASSED | 2026-09-09
TC-OEM-05 | API Security Ingest | Pipeline Ingest | API Gateway | Verify OWASP API Top 10 violation metrics are parsed per endpoint | API gateway logs | 1. Ingest broken object level authorization (BOLA) event 2. Verify API exposure score | API risk component reflects violation immediately | API security telemetry normalized | PASSED | 2026-09-09

## TC_Risk_and_Alerts
Test ID | Category | Persona / Role | Tenant Scope | Test Description | Pre-conditions | Execution Steps | Expected Result | Actual Result | Status | Execution Date
TC-RSK-01 | Formula Verification | Risk Calculation Engine | Asset Level | Verify multi-source weighted risk score matches mathematical model | Seeded asset findings (AppScan + WAF + DAM) | 1. Trigger risk recomputation 2. Compute expected formula score vs API output | Score equals exact weighted composite (0-100 scale) | Score matches deterministic calculation | PASSED | 2026-09-09
TC-RSK-02 | 14-Day Trend Continuity | Risk Trend Engine | Departmental | Verify 14-day rolling average risk trend contains no NaN or missing dates | Historical scoring dataset | 1. Fetch GET /api/v1/summary/trend 2. Verify array length and timestamp continuity | Continuous 14-day array with smooth delta progression | 14 data points returned with 0 gaps | PASSED | 2026-09-09
TC-ALT-01 | Critical Alert SLA | Alert Dispatcher | Estate-Wide | Verify Critical risk breach generates alert event within < 60 seconds | Simulate Critical RCE detection | 1. Ingest Critical vulnerability 2. Measure time until alert row is committed | Alert generated in < 60s with High SLA priority flag | Alert dispatched in 1.4 seconds | PASSED | 2026-09-09
TC-ALT-02 | Alert Scoping | SOC Lead | Home Affairs (Demo) | Verify DHA SOC team receives alerts strictly pertaining to Home Affairs assets | Broadcast alert across estate | 1. Query active alerts for soc-ha@ 2. Verify no Treasury alerts visible | Alerts filtered strictly by department tenancy | Tenancy filter applied correctly | PASSED | 2026-09-09

## TC_Compliance_AuditorGeneral
Test ID | Category | Persona / Role | Tenant Scope | Test Description | Pre-conditions | Execution Steps | Expected Result | Actual Result | Status | Execution Date
TC-AG-01 | Cryptographic Hash Chaining | Compliance Engine | Auditor-General Export | Verify exported security posture report generates verifiable SHA-256 hash | Export request initiated by compliance@ | 1. POST /api/v1/export/ag-pack 2. Verify SHA-256 header and database audit row | SHA-256 digest matches recomputed file checksum | Cryptographic hash verified | PASSED | 2026-09-09
TC-AG-02 | POPIA Data Masking | Privacy Filter | Public & Shared Views | Verify South African ID numbers and employee identities are redacted | Database rows with sensitive attributes | 1. Query public summary and unauthenticated preview 2. Inspect fields | PII masked with SHA hashes or asterisks | POPIA redaction confirmed | PASSED | 2026-09-09
TC-AG-03 | Immutable Audit Log | Audit Middleware | PostgreSQL Storage | Verify all login, role change, and tenant switch events log immutable audit records | Execute series of admin actions | 1. Check `audit_logs` table in PostgreSQL 2. Verify timestamps, IP, actor email, and actions | Complete sequential audit trail with zero dropouts | All actions logged immutably | PASSED | 2026-09-09

## TC_Frontend_UX
Test ID | Category | Persona / Role | Tenant Scope | Test Description | Pre-conditions | Execution Steps | Expected Result | Actual Result | Status | Execution Date
TC-UI-01 | Fluid Height Adaptation | All Viewports | Login Modal | Verify login modal dynamically fits on short laptop screens without cutting CTA | Viewport heights: 600px, 768px, 900px, 1080px | 1. Resize viewport to 600px height 2. Verify submit button remains visible or smoothly scrollable | Modal content fits within viewport height (0 overflow clipping) | Fluid clamp & scroll verified | PASSED | 2026-09-09
TC-UI-02 | Theme Contrast (Light/Dark) | All Themes | Landing & Dashboard | Verify WCAG 2.1 AA contrast compliance on buttons and text in Light & Dark modes | Toggle theme switch (☀ Light / 🌙 Dark) | 1. Measure contrast ratio of blue CTA on background 2. Measure text readability | Contrast ratio ≥ 4.5:1 in both modes | High contrast compliant | PASSED | 2026-09-09
TC-UI-03 | TypeScript Type Safety | Build System | Frontend Codebase | Verify zero TypeScript compilation errors across all components | Run `npx tsc --noEmit` | 1. Execute build compiler 2. Verify error count | Exit code 0, 0 TypeScript diagnostic errors | 0 errors (Exit code 0) | PASSED | 2026-09-09

## TC_PostSept9_Live_Verification
Test ID | Category | Persona / Role | Tenant Scope | Test Description | Pre-conditions | Execution Steps | Expected Result | Actual Result | Status | Execution Date
TC-POST9-01 | Live Ingestion Telemetry | Public / Unauthenticated | Whole Estate | Verify /api/v1/public/summary returns live ingestion totals without requiring authentication | PostgreSQL warehouse populated with AppScan findings | 1. Issue GET /api/v1/public/summary 2. Verify JSON structure contains findings, open findings, and severity map | HTTP 200 OK, total findings > 0, open count > 0, severity counts populated | HTTP 200 OK, total findings, open findings, and by_severity map verified | PASSED | 2026-09-10
TC-POST9-02 | AppScan Ingestion Query | AppSec Engineer | Department of Home Affairs (home-affairs-digital) | Verify /api/v1/findings?source=appscan&size=10 returns paginated AppScan findings with full metadata | Authenticated with Bearer token for appsec-ha@example.com | 1. Call GET /api/v1/findings?source=appscan&size=10 2. Inspect total, page count, and items array | HTTP 200 OK, paginated items with application_name, severity, CWE title, and discovery date | HTTP 200 OK, 50 findings total, 10 items returned on page 1 with full CWE attributes | PASSED | 2026-09-10
TC-POST9-03 | Critical Finding Extraction | SOC / AppSec Analyst | DHA Digital Scope | Verify /api/v1/findings?source=appscan&severity=critical filters strictly Critical findings with CVSS >= 9.0 and CVE tags | AppScan findings ingested in warehouse | 1. Call GET /api/v1/findings?source=appscan&severity=critical 2. Check CVSS score and CVE identifiers | Critical findings returned including SQL Injection (/bank/showtransactions, CVSS 9.8) with CVE tags | HTTP 200 OK, critical SQLi vulnerabilities returned with CVSS 9.8 and CVE correlation | PASSED | 2026-09-10
TC-POST9-04 | Remediation Metrics | Executive / AppSec | Estate-Wide / Scoped | Verify /api/v1/metrics/fix-rate calculates 30-day vulnerability remediation percentage | Warehouse contains both Open and Fixed status findings | 1. Call GET /api/v1/metrics/fix-rate with Bearer token 2. Inspect fix_rate numerical value | HTTP 200 OK, valid numerical percentage returned for 30-day fix rate | HTTP 200 OK, fix_rate metric successfully calculated and formatted | PASSED | 2026-09-10
TC-POST9-05 | WAF Edge Telemetry | AppSec Engineer | Department of Home Affairs | Verify /api/v1/metrics/waf-summary aggregates Imperva WAF blocks by attack type | Ingested WAF security event batch | 1. Call GET /api/v1/metrics/waf-summary 2. Inspect total blocks and by_type category breakdown | HTTP 200 OK, total blocks > 0 with SQLi, XSS, and bot classifications | HTTP 200 OK, WAF block classifications aggregated correctly | PASSED | 2026-09-10
TC-POST9-06 | API Security Telemetry | AppSec Specialist | Estate-Wide | Verify /api/v1/metrics/api-exposure audits shadow API endpoints and exposure vectors | API gateway telemetry ingested | 1. Call GET /api/v1/metrics/api-exposure 2. Inspect total endpoints and shadow API count | HTTP 200 OK, total endpoints and shadow API indicators returned | HTTP 200 OK, API security inventory and shadow metrics verified | PASSED | 2026-09-10
TC-POST9-07 | Tier 4 RBAC Authentication | SITA Superadmin | Nationwide (Tier 4) | Verify SITA superadmin (admin@example.com) authenticates with nationwide scope and transversal role claims | admin@example.com seeded with admin123 | 1. POST /api/v1/auth/login {email: admin@example.com, password: admin123} 2. Inspect JWT claims and department_ids | HTTP 200 OK, token issued with ALL_ROLES and empty department_ids (nationwide) | HTTP 200 OK, transversal superadmin authenticated with nationwide scope | PASSED | 2026-09-10
TC-POST9-08 | Tier 4 RBAC Authentication | SITA Transversal Admin | Nationwide (Tier 4) | Verify SITA transversal admin (transversal@example.com) authenticates across all 173 departments | transversal@example.com seeded with pass123 | 1. POST /api/v1/auth/login {email: transversal@example.com, password: pass123} 2. Verify user roles | HTTP 200 OK, token contains transversal-admin role claim | HTTP 200 OK, transversal admin authenticated with full ministerial scope | PASSED | 2026-09-10
TC-POST9-09 | Tier 2 RBAC Scoping | DHA Department Admin | Department of Home Affairs (home-affairs-digital) | Verify DHA dept admin (deptadmin-ha@example.com) authenticates strictly scoped to Home Affairs | deptadmin-ha@example.com seeded | 1. POST /api/v1/auth/login {email: deptadmin-ha@example.com, password: pass123} 2. Check department_ids and branch_ids | HTTP 200 OK, department_ids = ['home-affairs-digital'], branch_ids contains all 8 DHA branches | HTTP 200 OK, strictly scoped to DHA department and all 8 branches | PASSED | 2026-09-10
TC-POST9-10 | Tier 1 Operational Scoping | DHA SOC Analyst | DHA Operational Branch | Verify DHA SOC analyst (soc-ha@example.com) authenticates with soc role claim and DHA scope | soc-ha@example.com seeded | 1. POST /api/v1/auth/login with soc-ha@ credentials 2. Verify roles array in response | HTTP 200 OK, role includes soc, department_ids = ['home-affairs-digital'] | HTTP 200 OK, SOC analyst token issued with DHA scope | PASSED | 2026-09-10
TC-POST9-11 | Tier 1 Operational Scoping | DHA AppSec Specialist | DHA Operational Branch | Verify DHA AppSec engineer (appsec-ha@example.com) authenticates with appsec role claim | appsec-ha@example.com seeded | 1. POST /api/v1/auth/login with appsec-ha@ credentials 2. Verify roles array in response | HTTP 200 OK, role includes appsec, scoped to DHA | HTTP 200 OK, AppSec analyst token issued | PASSED | 2026-09-10
TC-POST9-12 | Tier 1 Operational Scoping | DHA DB Security Lead | DHA Operational Branch | Verify DHA DB Sec engineer (dbsec-ha@example.com) authenticates with dbsec role claim | dbsec-ha@example.com seeded | 1. POST /api/v1/auth/login with dbsec-ha@ credentials 2. Verify roles array in response | HTTP 200 OK, role includes dbsec, scoped to DHA | HTTP 200 OK, DB security analyst token issued | PASSED | 2026-09-10
TC-POST9-13 | Tenancy Hierarchy Traversal | Authenticated User | Whole Estate | Verify /api/v1/auth/tenancy provides full national structure (173 depts, 347 branches, 9 provinces) | Tenancy database populated | 1. GET /api/v1/auth/tenancy with auth header 2. Validate counts and DHA branch node | HTTP 200 OK, counts reflect 173 departments, 347 branches, 9 provinces, 8 DHA branches | HTTP 200 OK, hierarchy verified with accurate national and DHA branch counts | PASSED | 2026-09-10
TC-POST9-14 | Real Telemetry Verification | AppSec Analyst | Department of Home Affairs | Verify /api/v1/findings returns 50 live HCL AppScan findings with CWE classification | seed_real_appscan.py executed | 1. GET /api/v1/findings with appsec-ha@ token 2. Verify total findings and examine sample finding | 50 findings returned with attributes (SQLi on /bank/showtransactions, XSS on /search.jsp, Integer Overflow) | HTTP 200 OK, 50 real AppScan findings verified with full CWE metadata | PASSED | 2026-09-10
TC-POST9-15 | Database Activity Monitoring | DB Security Lead | DHA Database Tier | Verify /api/v1/metrics/dbsec/inventory returns 66 monitored database instances under DHA | Thales DAM telemetry seeded in database | 1. GET /api/v1/metrics/dbsec/inventory with dbsec-ha@ token 2. Count instances and verify Cassandra keyspaces | HTTP 200 OK, 66 instances returned including AUDIT_KEYSPACE, FLORENCE_CASSANDRA, USER_KEYSPACE | HTTP 200 OK, 66 monitored database instances verified with engine and classification metadata | PASSED | 2026-09-10
TC-POST9-16 | Security Operations Center Alerts | SOC Analyst | DHA SOC Queue | Verify /api/v1/alerts returns 47 active correlated security alerts across AppScan & DAM | Alert dispatcher pipeline executed | 1. GET /api/v1/alerts with soc-ha@ token 2. Verify total alert count and triage properties | HTTP 200 OK, 47 active alerts scoped to DHA with severity and status metadata | HTTP 200 OK, 47 active alerts returned and verified with status lifecycle support | PASSED | 2026-09-10
TC-POST9-17 | Regulatory Compliance Audit | Compliance Officer / SITA Superadmin | Nationwide (SITA Scope) | Verify /api/v1/compliance returns 82.9% overall score with 97/117 passed controls under POPIA framework | Compliance framework evaluation completed | 1. GET /api/v1/compliance with admin@ token 2. Validate framework, overall_score, and control counts | HTTP 200 OK, framework='POPIA', score=82.9%, passed_controls=97, total_controls=117 | HTTP 200 OK, POPIA compliance metrics verified (82.9% score, 97/117 passed controls) | PASSED | 2026-09-10
TC-POST9-18 | Compliance Trend History | Compliance Officer | Nationwide | Verify /api/v1/metrics/compliance/trend provides 360 continuous historical snapshots | Historical compliance snapshots generated | 1. GET /api/v1/metrics/compliance/trend 2. Count data_points in response | HTTP 200 OK, 360 data points returned without gaps or invalid records | HTTP 200 OK, 360 continuous snapshot data points verified | PASSED | 2026-09-10
TC-POST9-19 | Transversal User Administration | SITA Superadmin | Nationwide (Tiers 1-4) | Verify /admin/users returns all 20 accounts across all 4 tiers with unrestricted provisioning capability | Seed admin accounts executed | 1. GET /admin/users with admin@ token 2. Verify total accounts and inspect roles across all 4 tiers | HTTP 200 OK, 20 accounts returned covering SITA, National, Provincial, and Branch roles | HTTP 200 OK, 20 accounts verified across all 4 tiers with zero provisioning ceiling | PASSED | 2026-09-10
TC-POST9-20 | Scoped User Administration Ceiling | DHA Department Admin | DHA Only (Tier 2) | Verify /admin/users strictly restricts DHA deptadmin to 6 DHA personnel, preventing cross-tenant leakage | Authenticated with deptadmin-ha@example.com | 1. GET /admin/users with deptadmin-ha@ token 2. Verify count and ensure no non-DHA users are returned | HTTP 200 OK with strictly 6 DHA users (or HTTP 403 blocking transversal access) | Confirmed isolation: DHA admin strictly restricted to DHA users (0 non-DHA users visible) | PASSED | 2026-09-10
TC-POST9-21 | Zero Cross-Tenant Leakage Verification | DHA SOC Analyst | DHA Digital Scope | Verify soc-ha@ query to /api/v1/findings returns strictly DHA findings with 0 non-DHA finding leakage | Findings exist for DHA, Treasury, and other departments | 1. GET /api/v1/findings with soc-ha@ token 2. Scan all returned items for non-DHA department_ids | 100% of returned items have department_id='home-affairs-digital' or null; 0 cross-tenant leaks | PASSED: 0 non-DHA items detected among returned findings; 100% tenant isolation | PASSED | 2026-09-10
TC-POST9-22 | AppSec Sub-Metrics Telemetry | AppSec Analyst | Departmental Scope | Verify /metrics/appsec/waf, /metrics/appsec/api-exposure, and /metrics/appsec/fix-rate respond with HTTP 200 | Authenticated as AppSec | 1. Issue GET requests to all 3 AppSec sub-metrics endpoints 2. Verify HTTP status and payload formats | HTTP 200 OK on all 3 endpoints with valid telemetry payloads | HTTP 200 OK on all 3 sub-metrics endpoints | PASSED | 2026-09-10
TC-POST9-23 | SOC SLO Metrics Calculation | SOC Lead | DHA SOC Queue | Verify /api/v1/metrics/soc/slo calculates Mean Time to Detect (MTTD) and Mean Time to Respond (MTTR) | SOC alert data populated | 1. GET /api/v1/metrics/soc/slo with soc-ha@ token 2. Inspect SLO indicators in response | HTTP 200 OK, MTTD, MTTR, and SLA adherence metrics returned | HTTP 200 OK, SOC SLO metrics verified with sub-second retrieval latency | PASSED | 2026-09-10
TC-POST9-24 | Persona Discovery Metadata | Unauthenticated / Client | Whole Estate | Verify /api/v1/auth/demo-accounts provides metadata for all 11 demo personas with nationwide flags | Demo accounts registry loaded | 1. GET /api/v1/auth/demo-accounts 2. Verify list length, roles, and nationwide flags | HTTP 200 OK, all demo personas returned with accurate labels, roles, and department scoping | HTTP 200 OK, demo accounts metadata verified (11 personas, correct nationwide attributes) | PASSED | 2026-09-10
TC-POST9-25 | Telemetry Normalization Pipeline | Data Pipeline | Ingestion Normalizer | Verify test_normalize.py validates normalization of AppScan SAST/DAST fields to standardized schema | Python test environment | 1. Run python backend/test_normalize.py 2. Check exit code and test assertions | Exit code 0, all normalization mappings validated against SITA Lake specification | Exit code 0, normalized record fields match schema perfectly | PASSED | 2026-09-10
TC-POST9-26 | Lake Record Model Mapping | Ingestion Engine | Lake Data Model | Verify test_normalized_record.py and test_record_to_finding.py validate DB entity conversion | SQLAlchemy models defined | 1. Run python backend/test_normalized_record.py 2. Run python backend/test_record_to_finding.py | Exit code 0, record transformation and column types conform to PostgreSQL schema | Exit code 0, entity mappings and type coercions validated | PASSED | 2026-09-10
TC-POST9-27 | Frontend Demo Interceptor Routing | Browser Client | Frontend Application | Verify demoInterceptor.ts and demoApi.ts seamlessly handle client mock/live switching for DHA personas | Frontend running or static bundle loaded | 1. Inspect demo API interceptor route handlers 2. Verify fallback to demo dataset on disconnected mode | Interceptor transparently injects simulated DHA telemetry when backend is offline | Fluid fallback verified across all 5 DHA personas | PASSED | 2026-09-10
TC-POST9-28 | Production Distribution Build | Release Manager | Whole Frontend Bundle | Verify npm run build compiles clean production distribution in frontend/dist with 0 warnings | Node.js / Vite build environment | 1. Execute npm run build in /frontend 2. Inspect dist/ output and console log | Exit code 0, clean build output with zero fatal bundle warnings | Clean production build generated in dist/ (assets indexed and minified) | PASSED | 2026-09-10
TC-POST9-29 | Interactive Architecture & Presentation Integration | Executive Stakeholder | Executive Portal | Verify architecture.html and presentation.html render interactive multi-tier architecture diagram | Static HTML assets served in /frontend/public and /dist | 1. Load architecture.html and presentation.html in browser 2. Verify tier interactions | Interactive canvas renders 4-tier hierarchy and DHA test bed topology smoothly | Interactive architecture viewer and slide deck fully functional | PASSED | 2026-09-10