## Integration
HOW PHASE 13 INTEGRATES INTO THE EXISTING BACKEND PIPELINE · build 7-14 October 2026, Saturday 10 October included
The master flight plan (Phases 1-12) built a working warehouse and six dashboards. Phase 13 does not replace any of it - it adds the reporting intelligence layer the pipeline currently lacks, reading the warehouse the plan already built.
Master plan stage | Built by | Status today | Phase 13 relationship
1. OEM Ingestion | Phase 1-4 (AppScan, Imperva, API Sec) | Complete | Unchanged. No AI on the ingestion path.
2. Normalise & Stage | Phase 5 | Complete | Unchanged.
3. Warehouse + Risk Engine | Phase 6-7 (risk_engine.py:14, 4-signal weighted fusion) | Complete - 15 283 risk rows, 2 244 findings, 456 snapshots | READ-ONLY INPUT. Phase 13 reads warehouse.* through tenant_filter() and recomputes nothing.
4. FastAPI REST layer | Phase 9 (tenant_filter() at app/api/auth.py:210) | Complete - 6 role-gated endpoints | EXTENDED. Adds POST /api/v1/reports-ai/generate. One include_router line in app/main.py is the only edit to any existing file.
5. React dashboards | Phase 10 (6 dashboards, explanations.ts prose) | Complete | UNTOUCHED in the POC. The generated report is a separate surface; wiring it into DashHeader's children slot is Phase B.
6. Reports & exports | Phase 9 (CSV exports, AG attestation) | Complete | UNTOUCHED. build_attestation() stays pure and deterministic; the AI narrative never enters the signed attestation (D3).
REUSED, NOT REBUILT - every one of these already exists in the master plan's codebase
Existing asset | Location | Built by | How Phase 13 uses it
tenant_filter() | app/api/auth.py:210 | Phase 9 | DELEGATED, never reimplemented. It is opt-in per query, so Phase 13 makes scope a mandatory positional argument instead of a thing to remember.
canonical_json() / sha256_hex() | app/api/routers/exports_ag.py:48,58 | Phase 9 | Reused for scope_hash and fact_pack_hash. Reimplementing hashing is how two components end up disagreeing on what 'the same payload' means.
build_attestation() pattern | app/api/routers/exports_ag.py:62 | Phase 9 | The pure-builder shape the fact-pack builder copies: no DB, no session, no claims inside the builder, so it is unit-testable without a database.
CircuitBreaker | app/ingestion/circuit_breaker.py:11 | Phase 3 | Reused for the model gateway. Model down -> breaker opens -> deterministic fallback. Same failure handling the OEM connectors already use.
audit.action_audit | infrastructure/scripts/init-db.sql:120 | Phase 7 | The audit sink. One row per generation, same retention, AI rows never appear in an attestation.
_build_benchmark() peer blinding | app/api/routers/benchmark.py:46 | Phase 9 | PRECEDENT, not code reuse. A provincial exec sees peers as 'Peer Province A/B/C' with province_id null. That is claim-class blinding already working in deterministic Python.
DOMPurify sanitise | frontend/src/components/dashboard/ExplainOverlay.tsx:17 | Phase 10 | Phase B only. Narrative HTML already has a sanitising render path in production.
DashHeader children slot | frontend/src/components/dashboard/DashHeader.tsx:36 | Phase 10 | Phase B only. Mounts the AI control on all 6 dashboards with zero route changes.
NEW OBJECTS CREATED BY THIS ADDENDUM - nothing existing is modified except one line
backend/app/ai/ | 14 modules: permissions, scope, capability, accessors, context, disclosure, claims, prompt_builder, prompts/, gateway, settings, generate, fallback, verify | New namespace. ROLES_HIERARCHY is not modified; the permission namespace is additive.
backend/app/ai/routers/reports_ai.py | POST /generate, GET /available, GET /audit/{id} | All data routes POST, avoiding the demoInterceptor GET hijack in frontend/src/api/demoInterceptor.ts:34-42.
infrastructure/scripts/init-ai-schema.sql | schema ai, ai.report, 2 indexes | Kept out of warehouse.* so no existing reporting query can return an AI row by accident.
backend/tests/test_ai_*.py | S1 role matrix, S2 containment, S3 non-escalation, S4 claims, S6 signature, S7 capability, S8 numeral fidelity, S9 adversarial | CI-gated. S6 fails the build if a warehouse reader appears without a scope parameter.
app/main.py | ONE added line: app.include_router(reports_ai.router, prefix='/api/v1') | UNAVOIDABLE - it is the only router registration point in the codebase. Additive, no logic changed. Restated claim per R22; briefed to the client before the demo.
THE GAP PHASE 13 FILLS
- Today every insight a stakeholder sees is FIXED: a weighted sum (app/processing/risk_engine.py:14), a YAML rule evaluation (app/processing/alert_rules.yaml), or hand-authored HTML prose (frontend/src/data/explanations.ts buildExplain/buildLayman).
- That prose has already drifted. Verified against the live database, explanations.ts claims '60 departments' where the warehouse holds 173, and states database inventory and system metrics are 'not tracked by the backend yet' when warehouse.database_inventory holds 2 577 rows and system_metrics holds 95.
- Hand-authored narrative rots silently. A narrative generated from a fact pack cannot - which is the strongest practical argument for Phase 13, independent of any security argument.

## Task Breakdown (Granular)
GRANULAR TASK BREAKDOWN — 39 executable tasks, 7 to 16 October 2026
Lead Developer, G2: Takawira Mazando (11.75 PD / 94.0 h, 34 tasks) · Second Developer, G2: Peter Rashaya (1.50 PD / 12.0 h, 3 tasks) · Head of AI Research: Richard Masukume (advisory — 0.50 PD / 4.0 h in-register, T01 only) · Project Manager: Jerry (0.50 PD / 4.0 h, T36 evidence pack) · Register total: 39 tasks · 14.25 PD · 114.0 h. The two builders are peers and no task is co-owned. Saturday 10 October is worked by Takawira Mazando alone.
Every task is one editor session with a named artefact and a test that fails if the task is not done. Gate column references the exit criteria on 'The 9 Days' sheet. Hours column is PD x 8.0.
ID | Day | Task | Owner | Support | Artefact | Acceptance test | Gate | PD | Hours
DAY 1 — Wed 7 Oct · 2.00 PD · 12.5 h across 2 people
T01 | 1 | Pull qwen2.5:3b; verify it serves; measure CPU latency at max_tokens 300 / 600 / 900 | Richard Masukume | Takawira Mazando | backend/bench/probe_model.py, backend/bench/model_latency.md | `ollama list` shows qwen2.5:3b; latency table covers all three budgets; max_tokens chosen from the measurement, not guessed. 0.50 PD charged at 0.5 h on each non-Saturday day of the window (days 1,2,3,5,6,7,8,9) rather than as a 4.0 h block on day 1: the pull happens on day 1, the latency measurement is revisited as the cache and token budget settle, and the final table is closed into the evidence pack on day 9. | - | 0.5 | 4
T21 | 1 | gateway.py + app/ai/settings.py — httpx to Ollama, CircuitBreaker reuse, token budget | Takawira Mazando | Richard Masukume | backend/app/ai/gateway.py, backend/app/ai/settings.py | Reuses app/ingestion/circuit_breaker.py by identity. Day-1 setup ensures runtime is verified before prompt work. | - | 0.5 | 4
T02 | 1 | init-ai-schema.sql — schema ai, ai.report, 2 indexes, idempotent | Takawira Mazando | - | infrastructure/scripts/init-ai-schema.sql | Runs twice cleanly; table present in information_schema; model_id, model_digest, prompt_version, latency_ms, fallback_used all present (D5) | - | 0.25 | 2
T03 | 1 | Apply ai schema to the local sita instance; record the rehearsal | Takawira Mazando | - | migration rehearsal log | ai.report present in the live local database ¦¦ Effort carried in T02: same script, same instance. | - | 0 | 0
T04 | 1 | permissions.py — REPORT_AI_PERMISSIONS, ROLE_REPORT_AI, require_report_permission() | Takawira Mazando | - | backend/app/ai/permissions.py | Additive namespace; ROLES_HIERARCHY untouched; exec denied soc_shift_handover | GATE A | 0.5 | 4
T05 | 1 | permissions tests — unknown role 403, role count enumerated from ROLES_HIERARCHY | Takawira Mazando | - | backend/tests/test_ai_permissions.py | 14 roles enumerated, not the 11 in the original sheet; suite fails if the count changes | GATE A | 0.25 | 2
DAY 2 — Thu 8 Oct · 2.00 PD · 17.0 h across 2 people
T06 | 2 | scope.py — frozen ReportScope, resolve_report_scope(), scope_hash via canonical_json | Takawira Mazando | Richard Masukume | backend/app/ai/scope.py | Frozen (assignment raises); scope_hash order-independent and scope-sensitive; delegates to tenant_filter(), never re-implements it | GATE A | 0.5 | 4
T07 | 2 | Province-slug validation — fail LOUDLY on an unknown slug | Takawira Mazando | - | backend/app/ai/scope.py (validation branch) | province_ids=['gauteng'] raises a named error. Today it silently returns 0 rows, indistinguishable from correct scoping. | GATE A | 0.25 | 2
T08 | 2 | capability.py — introspection gate: SCOPABLE / REFERENCE / UNSCOPABLE | Takawira Mazando | Richard Masukume | backend/app/ai/capability.py | Every registered table classified. departments/branches/provinces are REFERENCE — labels only, never disclosed | GATE A | 0.25 | 2
T09 | 2 | capability.py — NEVER_READ denial for identity.users and audit.action_audit | Takawira Mazando | - | backend/app/ai/capability.py + test_ai_capability.py | Both raise at import. users carries password_hash and every user's tenancy assignment; action_audit carries every prior user's scope. No read path exists. ¦¦ Effort carried in T08: part of capability.py, same import assertion. | GATE A | 0 | 0
T10 | 2 | claims.py — ClaimClass, ROLE_CLAIMS, claim-pattern registry | Takawira Mazando | Richard Masukume | backend/app/ai/claims.py | exec holds none of cve_ids/alert_ids/owner_names/rule_ids. Matrix asserted equal to the signed D4 draft. No empty regex — an empty pattern matches everything. | GATE A | 0.75 | 6
T11 | 2 | disclosure.py — three DisclosureClass values + estate-wide summary | Takawira Mazando | Richard Masukume | backend/app/ai/disclosure.py | TENANT_SCOPED / ESTATE_WIDE / DERIVED_FROM_ESTATE_WIDE. Every risk_scores-sourced figure is DERIVED — the estate-wide component is inside fused_score itself. No REFERENCE value is ever tagged. | GATE A | 0.25 | 2
DAY 3 — Fri 9 Oct · 2.00 PD · 23.0 h across 4 people
T12 | 3 | accessors.py — read_risk_scores(scope, db), read_compliance(scope, db) | Takawira Mazando | Richard Masukume | backend/app/ai/accessors.py | scope is the FIRST POSITIONAL parameter on every reader. Aggregates in SQL — mappers.ts is NOT ported. | GATE B | 0.75 | 6
T13 | 3 | S6 structural test — signature inspection across accessors.py | Peter Rashaya | - | backend/tests/test_ai_accessors.py | 100% scope-first coverage, asserted by introspection. Fails the build if a warehouse reader appears without scope. Authored by the second developer against T12, which the Lead Developer wrote — the structural guarantee is checked by someone who did not build the readers. | GATE B | 0.25 | 2
T14 | 3 | Prompt builder — build_prompt(scope, report_type, pack); facts filtered to the claim set | Takawira Mazando | Richard Masukume | backend/app/ai/prompt_builder.py | pack.serialise(allowed=claims) — an unheld fact is ABSENT from the prompt, not merely forbidden. Scope block labelled for_attribution. Ground truth is NOT authored here: scope and capability delegate to tenant_filter() and SQL introspection, and the builder only serialises facts the pack already contains. | GATE B | 0.75 | 6
T15 | 3 | Role-injection harness — prove two roles produce different serialised prompts | Takawira Mazando | - | backend/tests/test_ai_prompt.py | Assertion is on allowed_claim_classes and on facts present, not string inequality | GATE B | 0.25 | 2
DAY 4 — Sat 10 Oct · 2.00 PD · 16.0 h across 1 person · WORKED BY TAKAWIRA ALONE
T16 | 4 | Prompt templates — executive_briefing.v1, compliance_status.v1 (code-assembled, versioned) | Takawira Mazando | Richard Masukume | backend/app/ai/prompts/*.v1.py | Immutable. Temperature 0.2. Constrained narrative output. 2 of the catalogue's 8 report types. | GATE C | 0.5 | 4
T17 | 4 | context.py — build_executive_context(): pure builder, SQL aggregation, fact_pack_hash | Takawira Mazando | Richard Masukume | backend/app/ai/context.py | Pure — testable with no database, the shape of build_attestation(). risk_scores.bucket read from the column, never recomputed. Unknown severities get an explicit unknown bucket, not the frontend's silent fold to info. | GATE C | 0.75 | 6
T18 | 4 | context.py — build_compliance_context() + estate-wide tagging | Takawira Mazando | - | backend/app/ai/context.py | 456 snapshots + 228 gaps tagged ESTATE_WIDE; the notice string comes from D-A6, defaulting to the envelope-only form until Compliance ratifies | GATE C | 0.25 | 2
T19 | 4 | Eval set — 3 personas x 2 report types = 6 fixtures with distinct scope_hash | Takawira Mazando | Richard Masukume | backend/tests/fixtures/ai_eval/*.json, test_ai_eval.py | All 6 scope_hash values distinct. No fixture figure exceeds its own pack max (live max 25.2, avg 7.46). Supported by Victoria — 0.75 PD of BA support, all of it delivered on Friday 9 Oct ahead of this task. | GATE C | 0.5 | 4
T20 | 4 | First end-to-end generation from a real fact pack | Takawira Mazando | Richard Masukume | - | A narrative is produced from live, scoped data. If the model failed to pull, the fallback produces it instead — identical numbers. ¦¦ Effort carried in T19: the first generation IS the Gate C evidence. | GATE C | 0 | 0
DAY 5 — Mon 12 Oct · 2.00 PD · 17.5 h across 3 people
T22 | 5 | generate.py — assemble → generate → verify → return; ONE filtered fact view for both renderers | Takawira Mazando | Peter Rashaya | backend/app/ai/generate.py | The fallback's input is the same object identity as the prompt's fact argument. It cannot disclose more than the model does. | GATE D | 0.75 | 6
T23 | 5 | verify.py — numeral fidelity + claim filter + scope containment + attribution | Peter Rashaya | Takawira Mazando | backend/app/ai/verify.py | THE most heavily tested module in the POC. Four checks, each with a positive and a negative test. Shares no code path with the prompt builder. Owned by the second developer: T14 and T16, the prompt builder and templates, are the Lead Developer's work, so the verifier is written by someone who did not write the prompt it polices. Tested by T31 and T32, which the Lead Developer wrote. | GATE D | 1 | 8
T24 | 5 | fallback.py — 2 deterministic Jinja2 templates | Takawira Mazando | - | backend/app/ai/fallback.py | Renders with NO model installed. Provable on 14 Oct regardless of the pull (R20). | GATE D | 0.25 | 2
T25 | 5 | Verifier failure paths return the template, never model text | Takawira Mazando | Peter Rashaya | test_ai_generate.py | Enforced by the return type being a union, not a nullable string. No partial credit, no warning-only mode (R6). ¦¦ Effort carried in T24: the union return type is the proof; the test just asserts it. | GATE D | 0 | 0
DAY 6 — Tue 13 Oct · 2.00 PD · 17.0 h across 3 people
T26 | 6 | reports_ai.py — POST /generate, GET /available, GET /audit/{id} | Takawira Mazando | Peter Rashaya | backend/app/ai/routers/reports_ai.py | All data routes POST — avoids the demoInterceptor GET hijack. /available returns only what THIS caller may request. | GATE E | 0.5 | 4
T27 | 6 | Response envelope — authorisation, disclosure, provenance, verification | Takawira Mazando | - | reports_ai.py (envelope) | All four blocks mandatory on every response, including the fallback path (model_id null, fallback_used true). ¦¦ Effort carried in T26: the envelope is part of the router response, not a separate artefact. | GATE E | 0 | 0
T28 | 6 | ActionAudit 'ai_report_generated' + ai.report write | Takawira Mazando | - | audit write in reports_ai.py | One audit row AND one ai.report row per generation, in ONE commit across two schemas. AI rows never appear in an attestation. | GATE E | 0.25 | 2
T29 | 6 | Register the router — ONE added line in app/main.py | Takawira Mazando | - | app/main.py (single line) | The only change to any existing file. app/main.py is the sole router registration point. ¦¦ Effort carried in T26: router registration is part of reports_ai.py delivery. | GATE E | 0 | 0
T30 | 6 | S2 scope containment + S3 non-escalation, live against the database | Peter Rashaya | Takawira Mazando | test_ai_containment.py | DHA soc 745 rows vs exec 2244, different scope_hash. Provincial persona widening scope yields expression.false() → 0, never estate-wide. Run live by the second developer against T06, T08 and T12, which the Lead Developer wrote — so the containment proof is not written by the author of the scope layer it proves. | GATE E | 0.25 | 2
T31 | 6 | S4 claims + S8 numeral fidelity + S7 capability, CI-gated | Takawira Mazando | Peter Rashaya | test_ai_claims.py, test_ai_verify.py, test_ai_capability.py | exec report contains zero CVE ids, alert ids, owner names, rule ids. Injected CVE id → sentence discarded. This suite is the principal test of T23, which Peter wrote — the harness and the verifier are not the same pair of hands. | GATE E | 0.5 | 4
T32 | 6 | S9 adversarial — scope widening, province naming, CVE injection, prompt injection via warehouse text | Takawira Mazando | Peter Rashaya | test_ai_adversarial.py | Every attempt rejected AT THE VERIFIER, even where the prompt permitted it. The prompt is not the control. | GATE E | 0.5 | 4
DAY 7 — Wed 14 Oct · 2.25 PD · 19.0 h across 3 people
T33 | 7 | Bucket-divergence tripwire — assert 0 rows with 30 < fused_score < 45 | Takawira Mazando | Richard Masukume | backend/tests/test_ai_bucket_band.py | Passes today (0 rows in band; all 15283 rows are 5.0-25.2). Failure message names all three bucket definitions: risk_engine.py:78, exports_ag.py:40, benchmark.py:38. Owned by the Lead Developer — this is a warehouse-layer regression guard. | FREEZE | 0.25 | 2
T38 | 7 | Integration smoke test — POST /api/v1/reports-ai/generate end-to-end with exec and soc roles | Takawira Mazando | Richard Masukume | backend/tests/test_ai_integration.py | Two roles, two scope_hash values, two distinct narratives. Asserts envelope structure, disclosure class, provenance block. Last regression gate before freeze. | FREEZE | 0.25 | 2
T34 | 7 | Full regression — ruff clean, pytest green, no existing test regressed | Takawira Mazando | Richard Masukume | - | Exactly the commands CI runs. The 11 existing test modules must stay green. | FREEZE | 0.5 | 4
T35 | 7 | Diff review — the restated non-interference claim | Takawira Mazando | Jerry | git diff main --stat | Additions only. ONE added line in app/main.py. Nothing in app/api/, app/processing/, app/tenant.py, app/models/ or the frontend. Reviewed with Richard, whose 0.5 h advisory on day 7 explicitly covers this diff — that review is the independent check on a task whose owner also wrote most of the code. ¦¦ Effort carried in T34: diff review executed as part of full regression freeze. | FREEZE | 0 | 0
T36 | 7 | Evidence pack — every gate evidenced by a named failing test | Jerry | Takawira Mazando | docs/G2_POC_2026-10-15/08_Evidence_Pack.md | Each gate traced to the test that fails without the corresponding work item. Plus the latency table and the diff. Owned by the Project Manager so the evidence is assembled by someone who did not write the code it certifies. | FREEZE | 0.5 | 4
T37 | 7 | Demo rehearsal end-to-end, timed, on day-7 hardware | Takawira Mazando | Richard Masukume | - | All 9 run-sheet items in order within 23 minutes. R21 is a CPU-latency risk; rehearsal on the freeze day is the only mitigation that works. | FREEZE | 0.5 | 4
T37b | 7 | Demo rehearsal AI controls & latency validation | Takawira Mazando | Richard Masukume | - | Validate prompt latency under 300/600 token limits; ensure fallback activation is seamless under model delay. | FREEZE | 0.25 | 2
|  | TOTAL | Takawira Mazando: 11.75 PD / 94.0 h · Peter Rashaya: 1.50 PD / 12.0 h · Richard Masukume: 0.50 PD (advisory) · Jerry: 0.50 PD |  |  |  |  | 14.25 | 114

## Role Split
ROLE ASSIGNMENT — why the split is drawn here
Dimension | Takawira Mazando | Peter Rashaya
| Takawira Mazando (Lead Developer, G2) | Peter Rashaya (Second Developer, G2)
Total build effort | 11.75 PD / 94.0 h | 1.50 PD / 12.0 h
Tasks owned | 34 | 3
Share of capacity | 167.9% of 7.00 PD — 38.0 h OVER the 56 h available | 21.4% of 7.00 PD
Accountable for | The deterministic backend, and the prompt layer built on top of it | The verifier and the containment proofs — the controls themselves
Owns | ai schema and DDL · Gate 1 RBAC · Gate 2 ReportScope · scope_hash · capability introspection and NEVER_READ denial · scope-first accessors · claim classes and ROLE_CLAIMS · disclosure classes · fact-pack builders · prompt builder and templates · model gateway · orchestration and fallback · REST router · response envelope · audit pair · adversarial suite · regression and diff | T13 the S6 structural test · T23 the four-check verifier · T30 live S2/S3 containment and non-escalation. Three tasks, 1.50 PD, all of them checks against code somebody else wrote.
Unit of work | A function that returns the same value twice | A test that fails when someone else's code is wrong
Why this split | Almost every deliverable is plumbing, and 94.0 h is what the plumbing actually costs inside 7 days. He carries the window. | The verifier must not be written by the author of the prompt it polices. T14 and T16 are Takawira's; T23 is Peter's. Claim 1 holds because of that separation.
Reporting line | Lead Developer, G2 | Second Developer, G2
Relationship | PEER. No task has both as owner. | PEER. Peter reports to Jerry as PM, not into Takawira.
Gate they own | GATE A · GATE B (prompt) · GATE C · GATE D (orchestration) · GATE E (router, adversarial) · FREEZE (regression, diff) | GATE B (S6, T13) · GATE D (verifier, T23) · GATE E (containment, T30)
What they must not do | Write or relax the verifier's patterns. T23 belongs to Peter; a check may be changed only in the same commit that changes the prompt it polices, never to make a generation succeed. | Touch the prompt builder, the templates, or the scope and capability layer. Peter is here to check Takawira's work, not to extend it.
Assumed available | 100%, 7-14 October including Saturday 10 October (D8) | 100%, 7-14 October (D8). His three tasks fall on Fri 9, Mon 12 and Tue 13 — he is not required on the weekend.
Effort | 11.75 PD over 7 build days = 1.68 PD/day (94.0 h, incl. 38.0 h overtime) | 1.50 PD over 3 build days = 0.21 PD/day (12.0 h)
Balance | Deliberately unbalanced, and recorded as such: one developer runs at 168% of his calendar for seven days. The register still fits (106.0 h of build demand against 112.0 h of capacity) but the float is Peter's unused time, which cannot be lent to a 16.0 h gate day. | Not spare capacity for someone else's problem. 78.6% of his 56 h was transferred to Takawira, which is why the transfer question was asked at all.
Peak day | 16.0 h on Day 2 (Thu 8, Gate A) and Day 4 (Sat 10, Gate C). Both are gate days, and Saturday has no second pair of eyes — that is the schedule risk this addendum is asking to be accepted (R18). | 8.0 h on Day 5 (Mon 12) — the verifier, the single most heavily tested module in the POC.
Advisory (not a build role) | Richard Masukume (Head of AI Research Department) holds no build tasks except T01 — the model pull and CPU latency measurement, 0.50 PD / 4.0 h, charged at 0.5 h on each non-Saturday day so no single day carries an artificial spike. He reviews at the gates, rehearses the AI controls with Takawira, and his day-7 advisory explicitly covers the freeze diff review (T35) — which is the independent check on a task whose owner wrote most of the code under review. 4.0 h of his time sits outside the build register. | Consequence of his advisory status: T05, T15, T34 and T35 become self-checks by one person. Richard's review, Victoria's BA support on T19 and Jerry owning the evidence pack (T36) are what stand in their place.
THE THREE CONTROL CLAIMS, AS THEY STAND IN THIS PLAN. 1. The verifier is not written by the prompt author — HOLDS: T23 (Peter) versus T14 and T16 (Takawira). 2. Ground truth is not authored by the model author — DOES NOT HOLD in the structural sense originally claimed, because Takawira owns the scope, capability, accessor and context layer AND the prompt builder. Restated: scope and capability DELEGATE to tenant_filter() and SQL introspection, neither of which can be widened from the prompt; the prompt builder only serialises facts the pack already contains (pack.serialise(allowed=claims)); and the containment proof is run live by T30, authored by Peter, not by the author of the prompt. 3. The structural filter cannot be bypassed by prompt text — HOLDS: pack.serialise() is a code boundary, not a rule in prose.

## Addendum B - Phase 13 Plan
ADDENDUM B TO THE HOSI-UNIFIED FLIGHT PLAN - PHASE 13: AI REPORT GENERATION (9-DAY PROOF OF CONCEPT)
Extends HOSI-UNIFIED_DATA_MANAGED_SERVICE_PROJECT_FLIGHT_PLAN_2026 (20 August 2026), Phases 1-12, 99 of 100 activities complete. This addendum ADDS Phase 13 as an additive backend stage - it does not amend, replace or renumber any existing phase. THE INTEGRATION: the master pipeline ends at Stage 4 (FastAPI REST layer, Phase 9). Every stakeholder figure today is fixed arithmetic or hand-authored prose. Phase 13 inserts an AI report-generation stage into the backend that reads FROM the warehouse built in Phase 7 and returns JSON to the existing Phase 10 dashboards. Compresses Addendum A (145.5 PD, 18 weeks) to 20.5 PD over 9 working days: build 7-14 October (Saturday 10 October is a working day, worked by Takawira Mazando alone), client demonstration 15 October 2026, close-out 16 October. Delivery: Takawira Mazando (Lead Developer, G2) and Peter Rashaya (Second Developer, G2) as builders, with Richard Masukume (Head of AI Research Department) advisory.
Lead Developer, G2 (builder) | Takawira Mazando - 11.75 PD / 94.0 h across 34 tasks, incl. 38.0 h overtime
Second Developer, G2 (builder) | Peter Rashaya - 1.50 PD / 12.0 h across 3 tasks (verifier and containment)
Head of AI Research (advisory) | Richard Masukume - 0.50 PD in-register (T01), plus 4.0 h of gate and freeze review
Governance / PM / Compliance | Jerry Mokone (Jerry owns T36), Victoria Nedombeloni, Kagiso Mokgofa - 3.75 PD, outside builder capacity
Total Activities | 57
Granular executable tasks | 39
Granular register in hours | 114.0 h (1 PD = 8.0 h)
Build demand vs capacity | 13.25 PD / 106.0 h against 14.00 PD / 112.0 h — float 0.75 PD / 6.0 h
Grand total, all resources | 124.0 h across 7-16 October
In scope (9 days) | 50
Deferred to Addendum A / Phase 2 | 6
Dropped by direction | 1
Total effort (person-days) | 20.5
Addendum A effort (person-days) | 145.5
Effort deferred | 125
Planned start | 2026-10-07
Client demonstration | 2026-10-15
Project Phases | Key Activity Description | Status | Pencentage | Start Date | End Date | Owner | Deliverable | Risks | Dependancies | Obstacles | Notes/Remarks/Comments | Ref | Effort (person-days) | Primary Owner | Phase No.
BLOCK 1 - Governance & Authorisation Foundation (compressed: 7-10 Oct)
BLOCK 1 - Governance & Authorisation Foundation (compressed: 7-10 Oct) | G2 plan drafted (alternative to the G1 AI-reporting section) and issued for approval | Completed | 1 | 2026-10-07 | 2026-10-07 | Takawira Mazando (Lead Developer, G2) | G2_AI_Report_Generation_Plan (proposal only, nothing built) |  | G1_AI_Integration_Plan.md |  | Already delivered: G2 plan + master AI integration plan + architecture assessment + ADR + execution plan. | 12.1 | 1 | Takawira Mazando | 12
BLOCK 1 - Governance & Authorisation Foundation (compressed: 7-10 Oct) | G2 plan review and approval - proceed on documented defaults | Not Started | 0.4 | 2026-10-07 | 2026-10-10 | Jerry (Project Manager) | Plan pack issued; defaults tabled for adoption at the 15 Oct demonstration | Stakeholder availability delays | 12.1 |  | Cannot close before the demo. Standing rule: a decision not amended is adopted as documented. | 12.2 | 0.5 | Jerry | 12
BLOCK 1 - Governance & Authorisation Foundation (compressed: 7-10 Oct) | Decision 1 - ai schema in the main DB or a separate reporting DB | Not Started | 1 | 2026-10-07 | 2026-10-08 | Takawira Mazando (Lead Developer, G2) | Written decision; DDL target confirmed | Delay blocks DDL in Phase 13.1 | Phase 12.2 |  | ANSWERED BY DEFAULT: schema 'ai' in the main database. A separate DB costs 4-6 PD of provisioning, none of it in this window. | 12.3 | 0.5 | Takawira Mazando | 12
BLOCK 1 - Governance & Authorisation Foundation (compressed: 7-10 Oct) | Decision 2 - estate-wide compliance disclosure: declare or block? | Not Started | 0 | 2026-10-07 | 2026-10-10 | Victoria Nedombeloni (Business Analyst / Compliance Lead) | Written decision on compliance_status report | Compliance data is structurally unscopable today | 12.2 |  | DEFAULT ADOPTED: declare ESTATE_WIDE. Proven live: 456 + 228 = 684 rows unscopable. This is the strongest demo item. | 12.4 | 0.5 | Victoria Nedombeloni | 12
BLOCK 1 - Governance & Authorisation Foundation (compressed: 7-10 Oct) | Decisions 3 and 5 - AG narrative stays separate from the attestation; ai.report audit retention | Not Started | 0 | 2026-10-07 | 2026-10-10 | Victoria Nedombeloni (Business Analyst / Compliance Lead) | Written decisions; retention aligned to audit.action_audit | Low risk: safe default is 'separate' | Phase 12.2 |  | DEFAULTS ADOPTED: narrative stays separate from the attestation; ai.report retention matches audit.action_audit. | 12.5 | 0.5 | Victoria Nedombeloni | 12
BLOCK 1 - Governance & Authorisation Foundation (compressed: 7-10 Oct) | Decision 4 - is DEPARTMENT_NAMES a safe claim class for exec estate-wide? | Not Started | 0 | 2026-10-07 | 2026-10-10 | Victoria Nedombeloni (Business Analyst / Compliance Lead) | Signed-off ROLE_CLAIMS matrix (section 6) | Provincial sensitivity | Phase 12.2 |  | DEFAULT ADOPTED: ROLE_CLAIMS signed exactly as drafted. Any widening needs fresh approval BEFORE implementation. | 12.6 | 0.5 | Victoria Nedombeloni | 12
BLOCK 1 - Governance & Authorisation Foundation (compressed: 7-10 Oct) | Decision 6 - model hosting: GPU CAPEX, sovereign cloud, or existing hardware | Not Started | 1 | 2026-10-07 | 2026-10-07 | Kagiso Mokgofa (Project Sponsor) | Hosting decision: self-hosted Ollama on existing hardware - zero CAPEX, zero procurement lead time | Procurement eliminated | Phase 12.2 |  | RESOLVED BY EVIDENCE. Ollama 0.35.1 already running (PID 27452). Replaces a 6 PD GPU provisioning activity. | 12.7 | 0.25 | Kagiso Mokgofa | 12
BLOCK 1 - Governance & Authorisation Foundation (compressed: 7-10 Oct) | Risk: decisions 1-6 not closed by the demonstration | Not Started | 0 | 2026-10-10 | 2026-10-10 | Jerry (Project Manager) | Weekly decision tracker; escalate to Sponsor on 14 Oct; build proceeds on stated defaults | Mitigation: default positions pre-agreed in G2 |  |  | Likelihood: Low. 6 of 7 are answered by evidence or default; all defaults are documented. | 12.8 | 0 | Jerry | 12
BLOCK 2 - Scoped Data Layer & Generation Engine (compressed: 7-12 Oct)
BLOCK 2 - Scoped Data Layer & Generation Engine (compressed: 7-12 Oct) | init-ai-schema.sql - schema ai, ai.report table and 2 indexes | Not Started | 0 | 2026-10-07 | 2026-10-07 | Takawira Mazando (Lead Developer, G2) | infrastructure/scripts/init-ai-schema.sql (19 columns, actor and scope_hash indexes); no change to warehouse.* | Alembic/DDL conflicts with concurrent dev branches | Decision 1 |  | Idempotent. Includes model_id, model_digest, prompt_version, latency_ms, fallback_used per D5. | 13.1 | 0.5 | Takawira Mazando | 13
BLOCK 2 - Scoped Data Layer & Generation Engine (compressed: 7-12 Oct) | permissions.py - per-report-type RBAC namespace (Gate 1) | Not Started | 0 | 2026-10-07 | 2026-10-08 | Takawira Mazando (Lead Developer, G2) | REPORT_AI_PERMISSIONS, ROLE_REPORT_AI (default-deny, 11 roles), require_report_permission() | ROLES_HIERARCHY must not be modified | Phase 12.2 |  | Additive namespace. 14 roles enumerated from ROLES_HIERARCHY, not the '11' in the original sheet. | 13.2 | 1 | Takawira Mazando | 13
BLOCK 2 - Scoped Data Layer & Generation Engine (compressed: 7-12 Oct) | scope.py - frozen ReportScope, ScopeClass, scope_hash (Gate 2) | Not Started | 0 | 2026-10-08 | 2026-10-08 | Takawira Mazando (Lead Developer, G2) | resolve_report_scope(claims) -> frozen ReportScope; canonical sha256 scope_hash; delegates to tenant_filter() | Province expansion must match tenant_filter() exactly | app/api/auth.py tenant_filter; JWT claims |  | Delegates to tenant_filter(); never re-implements it. Unknown province slug must fail LOUDLY. | 13.3 | 1.5 | Takawira Mazando | 13
BLOCK 2 - Scoped Data Layer & Generation Engine (compressed: 7-12 Oct) | Gate 1 / Gate 2 tests - unknown role 403, empty scope false(), scope_hash determinism | Not Started | 0 | 2026-10-08 | 2026-10-09 | Takawira Mazando (Lead Developer, G2) | pytest suite: unknown role -> 403; empty scope -> expression.false(); scope_hash stable |  | Phase 13.2, 13.3 |  | Proves GATE A. ¦¦ effort carried in 13.2 / 13.3 - the tests are how those two are proven | 13.4 | 0 | Takawira Mazando | 13
BLOCK 2 - Scoped Data Layer & Generation Engine (compressed: 7-12 Oct) | Apply ai schema to the local sita instance | Not Started | 0 | 2026-10-07 | 2026-10-07 | Takawira Mazando (Lead Developer, G2) | ai.report present in the local database; migration rehearsal log | Access to 192.168.101.0/24 depends on VPN (R1) | Phase 13.1 |  | LOCAL ONLY. VPN access to 192.168.101.0/24 (R12) is not required for the 15 Oct demo. ¦¦ effort carried in 13.1 - same script, applied to the same local instance | 13.5 | 0 | Takawira Mazando | 13
BLOCK 2 - Scoped Data Layer & Generation Engine (compressed: 7-12 Oct) | Risk: ReportScope diverges from tenant_filter() behaviour | Not Started | 0 | 2026-10-09 | 2026-10-09 | Takawira Mazando (Lead Developer, G2) | Parity test: ReportScope.tenant_filter() output equals app.api.auth.tenant_filter() for every persona | Mitigation: delegate, never re-implement |  |  | Mitigation: delegate, never re-implement. Parity asserted by 13.4. | 13.6 | 0 | Takawira Mazando | 13
BLOCK 2 - Scoped Data Layer & Generation Engine (compressed: 7-12 Oct) | accessors.py - scope-first warehouse readers (2 readers, not 5) | Not Started | 0 | 2026-10-08 | 2026-10-09 | Takawira Mazando (Lead Developer, G2) | Readers for findings, risks, alerts, compliance and benchmark (read-only reuse of _build_benchmark); scope is first positional arg | A forgotten tenant_filter silently returns the whole estate | Phase 13.3 |  | scope is FIRST POSITIONAL arg on every reader. Aggregates in SQL; mappers.ts is NOT ported. | 14.1 | 1 | Takawira Mazando | 14
BLOCK 2 - Scoped Data Layer & Generation Engine (compressed: 7-12 Oct) | S6 structural test - scope first positional parameter on every accessor | Not Started | 0 | 2026-10-09 | 2026-10-09 | Takawira Mazando (Lead Developer, G2) | Signature-inspection test, CI-gated (100% coverage) |  | Phase 14.1 |  | Signature-inspection test. Fails the build if a reader lacks scope. ¦¦ effort carried in 14.1 - S6 ships with the accessors it constrains | 14.2 | 0 | Takawira Mazando | 14
BLOCK 2 - Scoped Data Layer & Generation Engine (compressed: 7-12 Oct) | disclosure.py - THREE disclosure classes + capability introspection gate | Not Started | 0 | 2026-10-09 | 2026-10-09 | Takawira Mazando | TENANT_SCOPED / ESTATE_WIDE / DERIVED_FROM_ESTATE_WIDE; SCOPABLE/REFERENCE/UNSCOPABLE/NEVER_READ table classification | Depends on Decision 2 | Phase 12.4 |  | Adds ADR D-A3 (derived-estate-wide) and D-A5 (introspection + never-read denial) which the original 3.0 PD activity did not cover. | 14.3 | 0.75 | Takawira Mazando | 14
BLOCK 2 - Scoped Data Layer & Generation Engine (compressed: 7-12 Oct) | claims.py - ClaimClass and ROLE_CLAIMS matrix | Not Started | 0 | 2026-10-08 | 2026-10-09 | Takawira Mazando | Claim classes (9) mapped to exec, soc, appsec, dbsec, compliance | Depends on Decision 4 | Phase 12.6 |  | 9 claim classes. exec holds none of cve_ids/alert_ids/owner_names/rule_ids. Signed as drafted (D4). | 14.4 | 1 | Takawira Mazando | 14
BLOCK 2 - Scoped Data Layer & Generation Engine (compressed: 7-12 Oct) | context.py - pure fact-pack builders for 2 report types + fact_pack_hash | Not Started | 0 | 2026-10-10 | 2026-10-10 | Takawira Mazando (Lead Developer, G2) | Fact pack builders plus fact_pack_hash; identical pack feeds AI and fallback paths |  | Phase 14.1, 14.3 |  | 2 of the original 7 report types. Pure builders, testable without a DB, reusing canonical_json/sha256_hex. | 14.5 | 1 | Takawira Mazando | 14
BLOCK 2 - Scoped Data Layer & Generation Engine (compressed: 7-12 Oct) | Scope containment and non-escalation tests (S2, S3) on the fact pack | Not Started | 0 | 2026-10-10 | 2026-10-10 | Takawira Mazando (Lead Developer, G2) | Zero rows outside province-expanded set; out-of-scope request yields empty, never estate-wide | Test data may not cover cross-province cases | Phase 14.5 |  | Zero rows outside the province-expanded set; out-of-scope yields empty, never estate-wide. ¦¦ effort carried in 18.2 - same suites, same session | 14.6 | 0 | Takawira Mazando | 14
BLOCK 2 - Scoped Data Layer & Generation Engine (compressed: 7-12 Oct) | Risk: compliance tables remain unscopable | Not Started | 0 | 2026-10-10 | 2026-10-10 | Victoria Nedombeloni (Business Analyst / Compliance Lead) | Estate-wide disclosure rendered in every compliance response; tenancy columns are a separate approved change | Mitigation: explicit typed disclosure |  |  | Likelihood: High (structural). 9 of 16 warehouse tables are unscopable, verified by introspection. | 14.7 | 0 | Victoria Nedombeloni | 14
BLOCK 2 - Scoped Data Layer & Generation Engine (compressed: 7-12 Oct) | Model hosting - Ollama on existing hardware; pull qwen2.5:3b, benchmark CPU latency | Not Started | 0 | 2026-10-07 | 2026-10-07 | Richard Masukume (Head of AI Research Department) | Ollama serving qwen2.5:3b; latency table at 300/600/900 max_tokens | GPU / hosting lead time | Decision 6 |  | REPLACES the 6 PD GPU activity (12.7). Token cap decided day 1 on measured latency, not on rehearsal day. | 15.1 | 0.5 | Richard Masukume | 15
BLOCK 2 - Scoped Data Layer & Generation Engine (compressed: 7-12 Oct) | gateway.py - httpx to Ollama, CircuitBreaker reuse, token budget | Not Started | 0 | 2026-10-12 | 2026-10-12 | Takawira Mazando | Gateway with breaker states reused from connector framework; token budget enforced |  | Phase 15.1 (can stub) |  | Reuses app/ingestion/circuit_breaker.py. AI settings in app/ai/settings.py to hold non-interference to one line. | 15.2 | 0.5 | Takawira Mazando | 15
BLOCK 2 - Scoped Data Layer & Generation Engine (compressed: 7-12 Oct) | redaction.py - mandatory pre-egress PII scrubber (local model architecture) | Folded | 0 | 2026-10-10 | 2026-10-10 | Takawira Mazando (Lead Developer, G2) | Scrubber plus tests; zero cloud egress with local Ollama; raw_data excluded at fact pack assembly | Over-redaction degrades narrative quality |  |  | FOLDED into 14.5 / 15.4. Reassigned from Peter to Takawira. Model is local-only (localhost:11434, zero network egress); raw_data OEM payload dropped before prompt. | 15.3 | 0 | Takawira Mazando | 15
BLOCK 2 - Scoped Data Layer & Generation Engine (compressed: 7-12 Oct) | Role-aware prompt templates (2) + role-injection harness | Not Started | 0 | 2026-10-09 | 2026-10-10 | Takawira Mazando | build_prompt(scope, report_type, pack); templates versioned and immutable; facts filtered to the claim set BEFORE the prompt | Prompt injection via warehouse text fields | Phase 14.4 |  | 2 of the original 7 templates. Assembled by code, not hand-edited YAML. Proves GATE B. | 15.4 | 1.5 | Takawira Mazando | 15
BLOCK 2 - Scoped Data Layer & Generation Engine (compressed: 7-12 Oct) | generate.py - assembly, generation, verification, fallback orchestration | Not Started | 0 | 2026-10-12 | 2026-10-13 | Takawira Mazando (Lead Developer, G2) | End-to-end generate() with llm_enabled flag |  | Phase 15.2-15.4 |  | Model and fallback render from ONE filtered fact view, so the fallback cannot disclose more than the model. | 15.5 | 1 | Takawira Mazando | 15
BLOCK 2 - Scoped Data Layer & Generation Engine (compressed: 7-12 Oct) | Golden fact packs and prompt evaluation set - 3 personas x 2 report types | Not Started | 0 | 2026-10-10 | 2026-10-10 | Takawira Mazando | Golden packs for 7 report types per role; baseline quality scores |  | Phase 14.5 |  | All 6 scope_hash values distinct. No fixture figure exceeds its own pack max (live max 25.2, avg 7.46). | 15.6 | 0.75 | Takawira Mazando | 15
BLOCK 2 - Scoped Data Layer & Generation Engine (compressed: 7-12 Oct) | Risk: no model available | Not Started | 0 | 2026-10-07 | 2026-10-10 | Kagiso | Run on deterministic fallback; dev model on existing hardware; no scope impact | Mitigation: fallback is the safe default |  |  | CLOSED. Ollama is installed and running. Residual risk is the pull itself (R20); fallback is pre-agreed. | 15.7 | 0 | Kagiso | 15
BLOCK 3 - Verification, Fallback, API & Audit (compressed: 9-14 Oct)
BLOCK 3 - Verification, Fallback, API & Audit (compressed: 9-14 Oct) | verify.py - numeral fidelity check | Not Started | 0 | 2026-10-12 | 2026-10-12 | Peter Rashaya (Second Developer, G2) | Every figure in prose must exist in the fact pack; failure discards the model text | Too strict a verifier raises fallback rate | Phase 15.5 |  | Half of the 1.5 PD verifier effort. Every numeral in prose must exist in the fact pack. Owned by the second developer so the verifier is not written by the author of the prompt it polices. | 16.1 | 0.75 | Peter Rashaya | 16
BLOCK 3 - Verification, Fallback, API & Audit (compressed: 9-14 Oct) | Claim-permission filter with sentence discard | Not Started | 0 | 2026-10-12 | 2026-10-13 | Peter Rashaya (Second Developer, G2) | Regex scans (CVE ids, alert UUIDs, departments, rule ids, owners); discard not warn | Pattern coverage gaps | Phase 14.4 |  | Other half. Discard the sentence, not warn. | 16.2 | 0.75 | Peter Rashaya | 16
BLOCK 3 - Verification, Fallback, API & Audit (compressed: 9-14 Oct) | scope_hash match and cross-scope checks | Not Started | 0 | 2026-10-13 | 2026-10-13 | Takawira Mazando (Lead Developer, G2) | Verifier confirms envelope, cache key and audit row carry the same scope_hash |  | Phase 13.3 |  | scope_hash identical in envelope, cache key and audit row. ¦¦ effort carried in 16.1 - one verifier module | 16.3 | 0 | Takawira Mazando | 16
BLOCK 3 - Verification, Fallback, API & Audit (compressed: 9-14 Oct) | Deterministic Jinja2 fallback templates (2) | Not Started | 0 | 2026-10-13 | 2026-10-13 | Takawira Mazando (Lead Developer, G2) | Static templates driven by the same fact pack; fallback_used flag; works with no GPU |  | Phase 14.5 |  | Renders with NO model installed - provable on 14 Oct regardless of the pull. | 16.4 | 0.5 | Takawira Mazando | 16
BLOCK 3 - Verification, Fallback, API & Audit (compressed: 9-14 Oct) | Numeral-fidelity suite and claim-permission suite (S4) | Not Started | 0 | 2026-10-13 | 2026-10-13 | Takawira Mazando (Lead Developer, G2) | exec report contains zero CVE ids, alert ids or owner names |  | Phase 16.1, 16.2 |  | S4 claims + S8 numeral fidelity, CI-gated. ¦¦ effort carried in 18.2 | 16.5 | 0 | Takawira Mazando | 16
BLOCK 3 - Verification, Fallback, API & Audit (compressed: 9-14 Oct) | Adversarial prompt and injection testing | Not Started | 0 | 2026-10-13 | 2026-10-13 | Takawira Mazando (Lead Developer, G2) | Attempts to name other provinces or widen scope fail; findings logged |  | Phase 16.2 |  | Scope-widening, province-naming and CVE-injection attempts must all fail AT THE VERIFIER even where the prompt permitted them. ¦¦ effort carried in 18.2 | 16.6 | 0 | Takawira Mazando | 16
BLOCK 3 - Verification, Fallback, API & Audit (compressed: 9-14 Oct) | Risk: high fallback rate from over-strict verification | Not Started | 0 | 2026-10-14 | 2026-10-14 | Takawira Mazando (Lead Developer, G2) | Track fallback_rate per report type; tune patterns on golden packs | Mitigation: metrics and tuning in Phase 19 |  |  | Track fallback_rate per report type on the golden packs. | 16.7 | 0 | Takawira Mazando | 16
BLOCK 3 - Verification, Fallback, API & Audit (compressed: 9-14 Oct) | reports_ai.py - generate, available and audit endpoints | Not Started | 0 | 2026-10-13 | 2026-10-14 | Takawira Mazando (Lead Developer, G2) | POST /api/v1/reports-ai/generate; GET /available; GET /audit/{report_id}; POST avoids demoInterceptor GET hijack | Year-end compression (16 Dec holiday) | Phase 16 |  | POST /generate, GET /available, GET /audit/{id}. Adds ONE line to app/main.py - see 18.6. | 17.1 | 1 | Takawira Mazando | 17
BLOCK 3 - Verification, Fallback, API & Audit (compressed: 9-14 Oct) | Response envelope - authorisation, disclosure, provenance, verification | Not Started | 0 | 2026-10-13 | 2026-10-13 | Takawira Mazando (Lead Developer, G2) | Envelope returned on every response; authorisation and disclosure blocks mandatory |  | Phase 14.3 |  | authorisation, disclosure, provenance and verification blocks are mandatory on every response. ¦¦ effort carried in 17.1 - the envelope is part of the router response | 17.2 | 0 | Takawira Mazando | 17
BLOCK 3 - Verification, Fallback, API & Audit (compressed: 9-14 Oct) | Cache keyed on scope_hash | Deferred | 0 | 2026-10-14 | 2026-10-14 | Takawira Mazando (Lead Developer, G2) | Key = sha256(report_type + scope_hash + fact_pack_hash + prompt_version + model_digest) |  | Phase 13.3 |  | DEFERRED to Addendum A Phase 17. Cache isolation (S5) needs a Phase 2 window to be meaningful. | 17.3 | 0 | Takawira Mazando | 17
BLOCK 3 - Verification, Fallback, API & Audit (compressed: 9-14 Oct) | ActionAudit 'ai_report_generated' and ai.report writes | Not Started | 0 | 2026-10-14 | 2026-10-14 | Takawira Mazando (Lead Developer, G2) | One audit row per generation; AI rows never appear in an attestation |  | Phase 13.1 |  | One audit row AND one ai.report row per generation, in ONE commit across two schemas. | 17.4 | 0.5 | Takawira Mazando | 17
BLOCK 3 - Verification, Fallback, API & Audit (compressed: 9-14 Oct) | Minimal report viewer page | Dropped | 0 | 2026-10-14 | 2026-10-14 | Takawira Mazando (Lead Developer, G2) | NONE - dropped by direction. The agent is the reporting surface. | G2 defines no frontend scope; confirm at approval | Phase 17.1 |  | Dropped by Victoria's direction. The original sheet flagged it as a planning assumption. | 17.5 | 0 | Takawira Mazando | 17
BLOCK 3 - Verification, Fallback, API & Audit (compressed: 9-14 Oct) | AG attestation byte-identical regression test | Not Started | 0 | 2026-10-14 | 2026-10-14 | Takawira Mazando (Lead Developer, G2) | build_attestation() output identical to pre-change for the same inputs |  | Phase 17.4 |  | build_attestation() output byte-identical for the same inputs. ¦¦ effort carried in 18.2 | 17.6 | 0 | Takawira Mazando | 17
BLOCK 3 - Verification, Fallback, API & Audit (compressed: 9-14 Oct) | Risk: year-end freeze compresses Phase 17 | Not Started | 0 | 2026-10-14 | 2026-10-14 | Jerry (Project Manager) | Freeze 24 Dec-3 Jan assumed; viewer page can slip to Phase 18 without affecting the API | Likelihood: High |  |  | Not applicable. Year-end freeze is 3 months after this window. | 17.7 | 0 | Jerry | 17
BLOCK 3 - Verification, Fallback, API & Audit (compressed: 9-14 Oct) | S1 role matrix - 14 roles x 2 report types | Not Started | 0 | 2026-10-13 | 2026-10-13 | Takawira Mazando (Lead Developer, G2) | Exactly the section 5 matrix holds; unknown role -> 403 |  | Phase 17.1 |  | 14, not the 11 in the original sheet. The suite fails if the role count changes. ¦¦ effort carried in 18.2 | 18.1 | 0 | Takawira Mazando | 18
BLOCK 3 - Verification, Fallback, API & Audit (compressed: 9-14 Oct) | S2, S3, S4, S7, S8 suites CI-gated | Not Started | 0 | 2026-10-13 | 2026-10-14 | Takawira Mazando (Lead Developer, G2) | All six suites green in CI; S5 cache miss across scopes |  | Phase 17.3 |  | S5 cache isolation deferred with 17.3. ¦¦ effort carried in 19.3 - the evidence pack is the suites' output | 18.2 | 0 | Takawira Mazando | 18
BLOCK 3 - Verification, Fallback, API & Audit (compressed: 9-14 Oct) | Semgrep and Bandit scans on new modules | Not Started | 0 | 2026-10-14 | 2026-10-14 | Takawira Mazando (Lead Developer, G2) | Zero unhandled findings across app/ai and reports_ai.py |  | Phase 17 |  | ruff + semgrep/bandit on the new modules. ¦¦ effort carried in 18.6 - same diff-review session | 18.3 | 0 | Takawira Mazando | 18
BLOCK 3 - Verification, Fallback, API & Audit (compressed: 9-14 Oct) | Independent RBAC / tenancy security review | Deferred | 0 | 2026-10-14 | 2026-10-14 | SITA Information Security (Post-PoC Phase 2) | Review report; findings triaged | Reviewer availability | Phase 18.2 |  | DEFERRED. Zero SITA employees in build team. Formal SITA InfoSec review occurs in Phase 2 once solution is shipped to SITA environment post-PoC acceptance. | 18.4 | 0 | SITA InfoSec | 18
BLOCK 3 - Verification, Fallback, API & Audit (compressed: 9-14 Oct) | Load test (k6) and model-failure chaos test | Deferred | 0 | 2026-10-14 | 2026-10-14 | Takawira Mazando (Lead Developer, G2) | Breaker opens; fallback serves correct numbers; latency within agreed bound | Model latency (~6 s example in G2) under concurrency | Phase 15.1 |  | DEFERRED. k6 load test and chaos test need a stable endpoint; nothing is deployed to test against. | 18.5 | 0 | Takawira Mazando | 18
BLOCK 3 - Verification, Fallback, API & Audit (compressed: 9-14 Oct) | Diff review against main - restated non-interference claim | Not Started | 0 | 2026-10-14 | 2026-10-14 | Jerry (Project Manager) | git diff main shows additions only; ONE added line in app/main.py; nothing in app/api/, app/processing/, app/tenant.py, app/models/ or the frontend |  | Phase 18.2 |  | Original claim 'nothing existing modified' is not literally provable - app/main.py is the only router registration point. Restated per ADR D-A8 and briefed to the client in advance (R22). | 18.6 | 0.5 | Jerry | 18
BLOCK 3 - Verification, Fallback, API & Audit (compressed: 9-14 Oct) | Risk: critical finding from security review | Deferred | 0 | 2026-10-14 | 2026-10-14 | Jerry (Project Manager) | Deferred with 18.4 (independent security review) | Likelihood: Low |  |  | DEFERRED. 18.4 (independent security review) is deferred out of the 9-day window; risk cannot occur prior to the 15 Oct demonstration. | 18.7 | 0 | Jerry | 18
BLOCK 4 - Demo, Evidence & Sign-Off (compressed: 14-16 Oct)
BLOCK 4 - Demo, Evidence & Sign-Off (compressed: 14-16 Oct) | UAT with exec, SOC and compliance personas | Deferred | 0 | 2026-10-14 | 2026-10-14 | Jerry (Project Manager) | Signed UAT report per persona | Stakeholder availability delays | Phase 18 |  | DEFERRED. UAT requires UAT-ready documentation and a stable build; the 15 Oct session is a demonstration, not UAT. | 19.1 | 0 | Jerry | 19
BLOCK 4 - Demo, Evidence & Sign-Off (compressed: 14-16 Oct) | Demonstration defects triaged and logged | Not Started | 0 | 2026-10-15 | 2026-10-15 | Takawira Mazando (Lead Developer, G2) | Prompts v2; defect log closed |  | Phase 19.1 |  | Fix-forward after the demo, not during it. Carried to the Phase 2 estimate. ¦¦ effort carried in 19.5 | 19.2 | 0 | Takawira Mazando | 19
BLOCK 4 - Demo, Evidence & Sign-Off (compressed: 14-16 Oct) | Evidence pack - gate results, live outputs, latency table, diff | Not Started | 0 | 2026-10-14 | 2026-10-14 | Takawira Mazando (Lead Developer, G2) | docs/G2_POC_2026-10-15/08_Evidence_Pack.md |  |  |  | Every gate evidenced by a named test that fails without the corresponding work item. | 19.3 | 0.5 | Takawira Mazando | 19
BLOCK 4 - Demo, Evidence & Sign-Off (compressed: 14-16 Oct) | Production deployment and llm_enabled switch-on | Deferred | 0 | 2026-10-16 | 2026-10-16 | Takawira Mazando (Lead Developer, G2) | Deployed; feature flag enabled per environment | VPN access to 192.168.101.0/24 (R1) | Phase 19.2 |  | DEFERRED. Local/staging only for the demonstration. Production deployment is Phase 2. | 19.4 | 0 | Takawira Mazando | 19
BLOCK 4 - Demo, Evidence & Sign-Off (compressed: 14-16 Oct) | Acceptance sign-off against the POC criteria | Not Started | 0 | 2026-10-16 | 2026-10-16 | Jerry (Project Manager) | Signed POC acceptance checklist; Phase 2 re-estimate requested rather than a date |  | Phase 19.4 |  | Asks for a Phase 2 re-estimate, not a date. 29 Jan 2027 is withdrawn - it came from a 145.5 PD estimate that assumed GPU hosting. | 19.5 | 0.5 | Jerry | 19
BLOCK 4 - Demo, Evidence & Sign-Off (compressed: 14-16 Oct) | Schedule contingency buffer | Not Started | 0 | 2026-10-16 | 2026-10-16 | Jerry (Project Manager) | Reserved week; released if all gates are met |  |  |  | Day 9 is the only float and it is the close-out day. | 19.6 | 0 | Jerry | 19
BLOCK 2 - Scoped Data Layer & Generation Engine (compressed: 7-12 Oct)
BLOCK 2 - Scoped Data Layer & Generation Engine (compressed: 7-12 Oct) | capability.py - table introspection gate and NEVER_READ denial | Not Started | 0 | 2026-10-09 | 2026-10-09 | Takawira Mazando (Lead Developer, G2) | SCOPABLE / REFERENCE / UNSCOPABLE / NEVER_READ classification; identity.users and audit.action_audit raise at import; every registered table classified | R23 - agent-readable identity and authorisation surface if rushed |  |  | NEW - not in Addendum A. Neither G1 nor G2 considered that users (password_hash, roles, tenancy assignment) and action_audit (actor + every prior user's scope) are agent-readable. Highest-severity finding of the assessment. | 14.8 | 0.5 | Takawira Mazando | 14
BLOCK 4 - Demo, Evidence & Sign-Off (compressed: 14-16 Oct)
BLOCK 4 - Demo, Evidence & Sign-Off (compressed: 14-16 Oct) | Risk-bucket divergence tripwire test | Not Started | 0 | 2026-10-14 | 2026-10-14 | Takawira Mazando (Lead Developer, G2) | test asserts 0 rows with 30 < fused_score < 45; failure message names all three bucket definitions |  |  |  | NEW - not in Addendum A. risk_engine.py:78 uses safe<=30; exports_ag.py:40 and benchmark.py:38 use safe<45. Latent today (0 rows in band); G2 makes it detected rather than fixed. | 19.7 | 0.25 | Takawira Mazando | 19
TOTAL | [11 empty] | 57 activities | 20.5

## Effort & Capacity
Phase | Name | Start | End | Working days | Effort (PD) | Status | unit
12 | Governance, Approval & Decisions (Days 1-4) | 2026-10-07 | 2026-10-10 | 4 | 3.75 | In scope
13 | Authorisation Foundation - Gate 1 RBAC, Gate 2 ReportScope, ai schema (Days 1-3) | 2026-10-07 | 2026-10-09 | 3 | 3 | In scope
14 | Scoped Data Layer - accessors, fact pack, disclosure, claims (Days 2-5) | 2026-10-08 | 2026-10-10 | 3 | 4.25 | In scope
15 | Generation Engine - Ollama gateway, prompts, orchestration (Days 3-6) | 2026-10-07 | 2026-10-13 | 6 | 4.25 | In scope
16 | Verification & Deterministic Fallback (Days 5-7) | 2026-10-12 | 2026-10-14 | 3 | 2 | In scope
17 | REST Router, Envelope & Audit (Days 6-7) | 2026-10-13 | 2026-10-14 | 2 | 1.5 | In scope (part deferred)
18 | Verification Suites & Diff Review (Days 6-8) | 2026-10-13 | 2026-10-14 | 2 | 0.5 | In scope (part deferred)
19 | Demonstration, Evidence & Sign-Off (Days 8-9) | 2026-10-14 | 2026-10-16 | 3 | 1.25 | In scope (part deferred)
TOTAL effort in the 9-day window |  |  |  |  | 20.5 | pd
of which coarse activity build allocation |  |  |  |  | 16.75 | pd
of which granular engineering task effort (39 tasks) |  |  |  |  | 14.25 | pd
of which governance / compliance / sponsor / PM / advisory |  |  |  |  | 3.75 | pd
Addendum A baseline |  |  |  |  | 145.5 | pd
Effort deferred out of the 9-day window |  |  |  |  | 125 | pd
GRANULAR REGISTER (all 39 tasks, every owner) |  |  |  |  | 14.25 | pd
GRANULAR REGISTER in hours |  |  |  |  | 114 | h
BUILD CAPACITY: 2 developers x 7 build days at 100% |  |  |  |  | 14 | pd
BUILD CAPACITY in hours |  |  |  |  | 112 | h
Takawira Mazando: 11.75 PD / 94.0 h against 56.0 h available = 167.9% — OVER BY 38.0 h |  |  |  |  | 11.75 | pd
Peter Rashaya: 1.50 PD / 12.0 h against 56.0 h available = 21.4% |  |  |  |  | 1.5 | pd
Richard Masukume (advisory): 0.50 PD / 4.0 h in-register (T01), plus 4.0 h of gate, freeze and demo review outside the register |  |  |  |  | 0.5 | pd
Jerry: 0.50 PD / 4.0 h (T36 evidence pack) |  |  |  |  | 0.5 | pd
BUILD DEMAND (register, builders only) |  |  |  |  | 13.25 | pd
BUILD DEMAND in hours |  |  |  |  | 106 | h
SURPLUS / (SHORTFALL) on build demand vs capacity |  |  |  |  | 0.75 | pd
the same figure in hours — the real float |  |  |  |  | 6 | h
DAILY LOADING ACROSS THE WHOLE WINDOW (all resources, hours)
Wed 7 Oct — Takawira 12.0 · Richard 0.5 |  |  |  |  | 12.5 | h
Thu 8 Oct — Takawira 16.0 · Richard 1.0 |  |  |  |  | 17 | h
Fri 9 Oct — Takawira 14.0 · Peter 2.0 · Richard 1.0 · Victoria 6.0 |  |  |  |  | 23 | h
Sat 10 Oct — Takawira 16.0 [WORKED BY TAKAWIRA ALONE] |  |  |  |  | 16 | h
Mon 12 Oct — Takawira 8.0 · Peter 8.0 · Richard 1.5 |  |  |  |  | 17.5 | h
Tue 13 Oct — Takawira 14.0 · Peter 2.0 · Richard 1.0 |  |  |  |  | 17 | h
Wed 14 Oct — Takawira 14.0 · Jerry 4.0 · Richard 1.0 |  |  |  |  | 19 | h
Thu 15 Oct (demonstration) — Richard 1.5 |  |  |  |  | 1.5 | h
Fri 16 Oct (close-out) — Richard 0.5 |  |  |  |  | 0.5 | h
GRAND TOTAL across the window, every resource |  |  |  |  | 124 | h
Support, outside the build register: Victoria 6.0 h of BA prompt/eval work (all of it on Fri 9 Oct, ahead of T19) |  |  |  |  | 6 | h
Support, outside the build register: Richard 4.0 h of gate, freeze and demo review |  |  |  |  | 4 | h

## The 9 Days
The 9 days, gate by gate
Takawira Mazando (Lead Developer, G2) owns the deterministic backend and the prompt layer · Peter Rashaya (Second Developer, G2) owns the verifier and the containment proofs. Richard Masukume (Head of AI Research Department) is ADVISORY in this window: he holds T01 only, reviews at the gates and covers the freeze diff. Task IDs are granular - see the 'Task Breakdown (Granular)' sheet for artefacts and acceptance tests.
Day | Date | Takawira Mazando Lead Developer, G2 | Peter Rashaya Second Developer, G2 | Gate | Pass criteria
1 | Wed 7 Oct | Takawira Mazando: T21 gateway.py + app/ai/settings.py — httpx to Ollama, CircuitBreaker reuse, token budget · T02 init-ai-schema.sql — schema ai, ai.report, 2 indexes, idempotent · T03 Apply ai schema to the local sita instance; record the rehearsal · T04 permissions.py — REPORT_AI_PERMISSIONS, ROLE_REPORT_AI, require_report_permission · T05 permissions tests — unknown role 403, role count enumerated from ROLES_HIERARCHY · Peter Rashaya: 0.5 h of the T01 latency measurement | Peter Rashaya: — | - | Model serves and its latency is measured; ai.report exists in the live database; unknown role returns 403; 14 roles enumerated
2 | Thu 8 Oct | Takawira Mazando: T06 scope.py — frozen ReportScope, resolve_report_scope · T07 Province-slug validation — fail LOUDLY on an unknown slug · T08 capability.py — introspection gate: SCOPABLE / REFERENCE / UNSCOPABLE · T09 capability.py — NEVER_READ denial for identity.users and audit.action_audit · T10 claims.py — ClaimClass, ROLE_CLAIMS, claim-pattern registry · T11 disclosure.py — three DisclosureClass values + estate-wide summary · Peter Rashaya: 0.5 h of the T01 latency measurement | Peter Rashaya: — | GATE A | Unknown role 403 · empty scope expression.false() · unknown province slug raises LOUDLY · NEVER_READ raises at import · claim patterns non-empty · exec holds no cve_ids/alert_ids/owner_names/rule_ids
3 | Fri 9 Oct | Takawira Mazando: T12 accessors.py — read_risk_scores · T14 Prompt builder — build_prompt · T15 Role-injection harness — prove two roles produce different serialised prompts · Peter Rashaya: 0.5 h of the T01 latency measurement | Peter Rashaya: T13 S6 structural test — signature inspection across accessors.py | GATE B | S6 green - every accessor takes scope first (T13, written by Peter against Takawira's T12) · capability() classifies every registered table · two roles produce different allowed_claim_classes and different facts
4 | Sat 10 Oct | Takawira Mazando: T16 Prompt templates — executive_briefing.v1, compliance_status.v1 · T17 context.py — build_executive_context · T18 context.py — build_compliance_context · T19 Eval set — 3 personas x 2 report types = 6 fixtures with distinct scope_hash · T20 First end-to-end generation from a real fact pack | Peter Rashaya: — | GATE C - CUT TRIGGER | First generation from a real fact pack · 6 eval fixtures with distinct scope_hash · no fixture figure exceeds its own pack max. WORKED BY TAKAWIRA ALONE — no peer review available on this gate day (R18)
5 | Mon 12 Oct | Takawira Mazando: T22 generate.py — assemble → generate → verify → return; ONE filtered fact view for both renderers · T24 fallback.py — 2 deterministic Jinja2 templates · T25 Verifier failure paths return the template, never model text | Peter Rashaya: T23 verify.py — numeral fidelity + claim filter + scope containment + attribution | GATE D | Verifier discards an ungrounded numeral AND an unheld claim class · fallback renders from the identical filtered fact view · any failure returns the template, never model text. The verifier is Peter's; the prompt that feeds it is Takawira's
6 | Tue 13 Oct | Takawira Mazando: T26 reports_ai.py — POST /generate, GET /available, GET /audit/{id} · T27 Response envelope — authorisation, disclosure, provenance, verification · T28 ActionAudit 'ai_report_generated' + ai.report write · T29 Register the router — ONE added line in app/main.py · T31 S4 claims + S8 numeral fidelity + S7 capability, CI-gated · T32 S9 adversarial — scope widening, province naming, CVE injection, prompt injection via warehouse text | Peter Rashaya: T30 S2 scope containment + S3 non-escalation, live against the database | GATE E | DHA soc 745 rows vs exec 2244, different scope_hash (T30, Peter) · provincial widening yields expression.false() → 0 · scope-widening, province-naming and CVE-injection all rejected AT THE VERIFIER
7 | Wed 14 Oct | Takawira Mazando: T33 Bucket-divergence tripwire — assert 0 rows with 30 < fused_score < 45 · T38 Integration smoke test — POST /api/v1/reports-ai/generate end-to-end with exec and soc roles · T34 Full regression — ruff clean, pytest green, no existing test regressed · T35 Diff review — the restated non-interference claim · T37 Demo rehearsal end-to-end, timed, on day-7 hardware · T37b Demo rehearsal AI controls & latency validation · Peter Rashaya: 0.5 h of the T01 latency measurement | Peter Rashaya: — | FREEZE 17:00 | ruff clean · full pytest green with no existing test regressed · diff is additions only and independently reviewed by Richard · tripwire passes · integration smoke test green · evidence pack assembled by Jerry (T36) · run sheet rehearsed and timed
8 | Thu 15 Oct | - | - |  | CLIENT DEMONSTRATION - 23-minute run sheet. Richard supports (1.5 h advisory)
9 | Fri 16 Oct | Defect triage; evidence pack finalised | - |  | POC acceptance checklist signed · Phase 2 re-estimate requested · 29 Jan 2027 withdrawn · T01 latency table closed by Richard (0.5 h)

## Demo Run Sheet 15 Oct
Demonstration run sheet - Thursday 15 October 2026
23 minutes. Every item runs against the live database - no mocks, no synthetic data.
Min | Demonstration | What it proves | Live data
0-3 | exec -> executive_briefing. Model-generated narrative over the live estate | The agent works, on real data | 15 283 risk rows, 2 244 findings
3-5 | Response envelope: authorisation, disclosure, provenance, verification | Authorisation is part of the contract, not metadata | scope_hash shown
5-8 | exec -> compliance_status. disclosure shows estate_wide 456 and derived_estate_wide | The design surfaces its own limits instead of hiding them | 456 snapshots + 228 gaps, unscopable
8-10 | exec -> soc_shift_handover -> 403 | Gate 1 default-deny | No rows returned
10-14 | Role-aware prompting, live: same report type, exec vs soc, side by side | Different claim classes produce materially different text | exec holds no cve_ids; soc does
14-17 | DHA soc vs exec: 745 vs 2 244 rows, different scope_hash | Tenancy containment (S2) | home-affairs-digital
17-19 | Provincial persona attempts to widen scope -> fails closed to empty | Non-escalation (S3). Never estate-wide | expression.false() -> 0
19-21 | Claim filter catches an injected CVE id -> sentence discarded | The verifier, not the prompt, is the control | Regex discard
21-23 | git diff main --stat. One added line in app/main.py, additions only | Non-interference, stated precisely | Briefed in advance (R22)
NOT DEMONSTRATED IN THE POC
- Cache isolation (S5) - no cache is built in the 9-day window. The cache-keying test that was drafted against it is not in this register, because there is nothing to collide.
- Independent RBAC/tenancy security review - no reviewer could be sourced and briefed in 9 days
- k6 load test and model-failure chaos test - nothing is deployed to test against
- UAT - the 15 October session is a demonstration, not user acceptance testing
- Production deployment - local/staging only
- 5 of the 7 report types - the catalogue is 8, the POC ships 2

## Assumptions
Assumptions & standing defaults
# | Assumption | Consequence if false
1 | Takawira Mazando (Lead Developer, G2) is available at 100% for 7-14 October INCLUDING SATURDAY 10 OCTOBER, and carries 11.75 PD / 94.0 h - 168% of his 56 h, i.e. 38.0 h of overtime | The build does not fit inside the window. The Gate C cut trigger is the pre-agreed release valve; it is decided Saturday 10 Oct, on the day Takawira works alone.
2 | Saturday 10 October is a working day worked by Takawira Mazando ALONE. Peter, Victoria and Richard are all off. Peter's three tasks fall on Fri 9, Mon 12 and Tue 13 | Gate C falls on a single-person day with no peer review available. Richard's advisory review moves to Monday 12 Oct; the containment proofs land Tuesday 13 Oct and act as the real check.
3 | Peter Rashaya (Second Developer, G2) IS available for 7-14 October and returns to this window, taking the three verification tasks T13, T23 and T30 - 1.50 PD / 12.0 h. His three are Friday, Monday, Tuesday; he is not required on the weekend | Addendum A's 61 PD assignment to him stands as re-baselined here, not as deleted. If he cannot return, the verifier has no independent author and claim 1 fails.
4 | Richard Masukume (Head of AI Research Department) is ADVISORY for this window: T01 only (0.50 PD / 4.0 h, charged 0.5 h on each non-Saturday day), plus 4.0 h of gate, freeze and demonstration review outside the build register | T05, T15, T34 and T35 become self-checks by one person. Richard's freeze-diff review, Victoria's BA support on T19 and Jerry's evidence pack (T36) are the mitigations.
5 | The two BUILDERS are peers. No task is co-owned, and neither may take the other's work. The verifier (T23) is Peter's; the prompt builder and templates it polices (T14, T16) are Takawira's | Co-ownership, or one person writing both sides of a control, would defeat the purpose of having two developers at all.
6 | Ollama 0.35.1 remains running; qwen2.5:3b pulls successfully | Fallback-only demo with identical numbers. Pre-agreed degradation, not a failure.
7 | Local PostgreSQL 18.1 (sita) is available; no VPN to 192.168.101.0/24 is needed | R12 becomes blocking. The demo moves to wherever the database is reachable.
8 | No SA public holiday falls between 7 and 16 October 2026 | One build day lost from a window with 6.0 h of float.
9 | The delivery team contains ZERO SITA employees; SITA is the client/customer | Delivery is executed 100% by vendor team (Takawira, Peter, Richard, Jerry, Victoria, Kagiso). No dependency on SITA personnel availability during the 7-14 Oct build.
10 | The demonstration runs against local/staging vendor environment, not SITA infrastructure | Solution is packaged and shipped to SITA environment in Phase 2 only after PoC demonstration and formal acceptance by SITA on 15 Oct 2026.
11 | Docker remains unavailable; native PostgreSQL is used | No impact - nothing is containerised for the POC.
12 | STANDING RULE: a decision not amended on 15 October is adopted as documented | None. This is the mechanism that makes a 9-day window possible at all.
13 | Decisions default: ai schema in main DB; disclose ESTATE_WIDE; narrative separate from the attestation; ROLE_CLAIMS as drafted; ai.report retention matches action_audit; Ollama self-hosting | Each default is documented and defensible, so a missed deadline is not a blocker.
14 | Non-interference is restated: one added line in app/main.py, additions only | If the original 'nothing existing modified' claim is presented, it fails on a projector (R22).
15 | The master flight plan (Phases 1-12) is unchanged and stays at 99/100 complete. Phase 13 is ADDED, not a replacement of any existing phase | If Phase 13 were intended to alter Phases 1-12, the master plan needs re-baselining first.
16 | The existing backend pipeline is integrated, not bypassed: Phase 13 reads warehouse.* (Phase 7) through tenant_filter() (Phase 9) and returns JSON to the existing Phase 10 dashboards | A parallel AI stack reading the database directly would reintroduce unscoped reads - the exact defect tenant_filter's opt-in design invites.

## Risk Register
Risk register - 9-day window. Score = Likelihood x Impact. Critical >= 15, High >= 10, Medium >= 5.
ID | Risk | L | I | Score | Rating | Mitigation | Owner | Phase | Status
R18 | One developer runs the window at 168%. Takawira carries 94.0 h against 56 h - 38.0 h of overtime - with 16.0 h peaks on BOTH gate days (Thu 8 and Sat 10), and Sat 10 has no peer review | 5 | 5 | 25 | Critical | Recorded and accepted rather than hidden: Peter owns the verifier and the containment proofs so the heaviest load is the deterministic backend; the pre-agreed cut trigger at GATE C on Saturday 10 Oct drops the compliance_status report type, decided on the day, not discovered on Wed 14; Richard's freeze-diff review and Jerry's evidence pack are outside Takawira's hands. | Kagiso, Jerry | All | Open - accepted
R09 | Verification is concentrated in one person at 21% utilisation while the other runs at 168%. T05, T15, T34 and T35 are self-checks by the same author as the code they check | 5 | 4 | 20 | Critical | T13, T23 and T30 are Peter's, against code Takawira wrote - three independent checks, not one. Richard's 0.5 h day-7 advisory explicitly covers the T35 diff review. Victoria's 6.0 h of BA support lands on Fri 9, and Jerry owns the evidence pack (T36), so the certification is written by someone who did not build the code. | Jerry | All | Open
R23 | identity.users and audit.action_audit become agent-readable if the capability gate is rushed | 3 | 5 | 15 | Critical | T09 acceptance: NEVER_READ raises at import; a test asserts no accessor references either model | Takawira | 13-14 | Open
R02 | Compliance data is structurally unscopable - 684 rows, no tenancy columns | 5 | 3 | 15 | Critical | Typed three-class disclosure enforced by the verifier. Tenancy columns are a separate approved change (D2) | Compliance | 14 | Accepted by design
R22 | Non-interference is not literally provable; one include_router line is unavoidable | 4 | 3 | 12 | High | Restate the claim per ADR D-A8 and brief the client BEFORE 15 Oct | Jerry | 18 | Open
R05 | Narrative discloses identifiers the role may not see (CVE, alert, owner) | 3 | 4 | 12 | High | Post-generation claim filter with sentence discard; S4 suite; facts filtered to the claim set before the prompt | Peter | 16 | Open
R04 | Model states a figure that is not in the fact pack | 3 | 4 | 12 | High | Numeral-fidelity check; discard and return the deterministic template | Peter | 16 | Open
R08 | Prompt injection via free-text warehouse fields | 3 | 4 | 12 | High | Constrained decode; verifier independent of the prompt; adversarial suite on day 6 | Peter | 16 | Open
R20 | Model not pulled - the download is on the critical path | 3 | 3 | 9 | Medium | Pull day 1. The fallback serves identical numbers. Pre-agreed degradation. | Richard | 15 | Open
R21 | CPU-only inference latency under demo conditions | 4 | 2 | 8 | Medium | Token cap decided DAY 1 on measured latency; T01's 0.5 h daily slices let the measurement be revisited as the token budget settles; rehearse end-to-end on day 7 | Richard | 15 | Open
R03 | A warehouse reader is written without scope, leaking estate-wide rows | 2 | 5 | 10 | High | Scope is the first positional argument; the S6 signature test fails the build | Takawira | 14 | Open
R-AI-11 | Silent estate-wide compliance data presented as department-scoped | 4 | 5 | 20 | Critical | Typed three-class disclosure; attribution check in the verifier; Gate 1 default-deny | Compliance | 14 | Open
R17 | Stakeholder availability for decisions and the demonstration | 3 | 3 | 9 | Medium | Named owners and dates; defaults pre-agreed so a missed deadline is not a blocker | Jerry | 12 | Open
R25 | Bucket-definition divergence goes live (30 < fused_score < 45) | 2 | 3 | 6 | Medium | Tripwire test makes it detected. Consolidation is Phase 0 work, not G2. | Takawira | 19 | Open
R12 | VPN access to 192.168.101.0/24 blocks deployment | 1 | 3 | 3 | Low | Not needed - the demo runs against the local sita instance | Takawira | 13 | Closed by scope

## Gantt
Daily Gantt - 9 working days, 7 to 16 October 2026 (Saturday 10 Oct is a working day)
Ref | Activity | Owner | D1 Wed 7 | D2 Thu 8 | D3 Fri 9 | D4 Sat 10 | D5 Mon 12 | D6 Tue 13 | D7 Wed 14 | D8 Thu 15 DEMO | D9 Fri 16
BLOCK 1 - Governance & Authorisation Foundation
12.1 | G2 plan drafted (alternative to the G1 AI-reporting section) and issued for approval | Takawira Mazando | █
12.2 | G2 plan review and approval - proceed on documented defaults | Jerry | █ | █ | █ | █
12.3 | Decision 1 - ai schema in the main DB or a separate reporting DB | Takawira Mazando | █ | █
12.4 | Decision 2 - estate-wide compliance disclosure: declare or block? | Victoria Nedombeloni | █ | █ | █ | █
12.5 | Decisions 3 and 5 - AG narrative stays separate from the attestation; ai.report audit retention | Victoria Nedombeloni | █ | █ | █ | █
12.6 | Decision 4 - is DEPARTMENT_NAMES a safe claim class for exec estate-wide? | Victoria Nedombeloni | █ | █ | █ | █
12.7 | Decision 6 - model hosting: GPU CAPEX, sovereign cloud, or existing hardware | Kagiso Mokgofa | █
12.8 | Risk: decisions 1-6 not closed by the demonstration | Jerry |  |  |  | █
BLOCK 2 - Scoped Data Layer & Generation Engine
13.1 | init-ai-schema.sql - schema ai, ai.report table and 2 indexes | Takawira Mazando | █
13.2 | permissions.py - per-report-type RBAC namespace (Gate 1) | Takawira Mazando | █ | █
13.3 | scope.py - frozen ReportScope, ScopeClass, scope_hash (Gate 2) | Takawira Mazando |  | █
13.4 | Gate 1 / Gate 2 tests - unknown role 403, empty scope false(), scope_hash determinism | Takawira Mazando |  | █ | █
13.5 | Apply ai schema to the local sita instance | Takawira Mazando | █
13.6 | Risk: ReportScope diverges from tenant_filter() behaviour | Takawira Mazando |  |  | █
14.1 | accessors.py - scope-first warehouse readers (2 readers, not 5) | Takawira Mazando |  | █ | █
14.2 | S6 structural test - scope first positional parameter on every accessor | Takawira Mazando |  |  | █
14.3 | disclosure.py - THREE disclosure classes + capability introspection gate | Takawira Mazando |  |  | █
14.4 | claims.py - ClaimClass and ROLE_CLAIMS matrix | Takawira Mazando |  | █ | █
14.5 | context.py - pure fact-pack builders for 2 report types + fact_pack_hash | Takawira Mazando |  |  |  | █
14.6 | Scope containment and non-escalation tests (S2, S3) on the fact pack | Takawira Mazando |  |  |  | █
14.7 | Risk: compliance tables remain unscopable | Victoria Nedombeloni |  |  |  | █
15.1 | Model hosting - Ollama on existing hardware; pull qwen2.5:3b, benchmark CPU latency | Richard Masukume | █
15.2 | gateway.py - httpx to Ollama, CircuitBreaker reuse, token budget | Takawira Mazando |  |  |  |  | █
15.3 | redaction.py - mandatory pre-egress PII scrubber (local model architecture) | Takawira Mazando |  |  |  | █
15.4 | Role-aware prompt templates (2) + role-injection harness | Takawira Mazando |  |  | █ | █
15.5 | generate.py - assembly, generation, verification, fallback orchestration | Takawira Mazando |  |  |  |  | █ | █
15.6 | Golden fact packs and prompt evaluation set - 3 personas x 2 report types | Takawira Mazando |  |  |  | █
15.7 | Risk: no model available | Kagiso | █ | █ | █ | █
BLOCK 3 - Verification, Fallback, API & Audit
16.1 | verify.py - numeral fidelity check | Peter Rashaya |  |  |  |  | █
16.2 | Claim-permission filter with sentence discard | Peter Rashaya |  |  |  |  | █ | █
16.3 | scope_hash match and cross-scope checks | Takawira Mazando | [5 empty] | █
16.4 | Deterministic Jinja2 fallback templates (2) | Takawira Mazando | [5 empty] | █
16.5 | Numeral-fidelity suite and claim-permission suite (S4) | Takawira Mazando | [5 empty] | █
16.6 | Adversarial prompt and injection testing | Takawira Mazando | [5 empty] | █
16.7 | Risk: high fallback rate from over-strict verification | Takawira Mazando | [6 empty] | █
17.1 | reports_ai.py - generate, available and audit endpoints | Takawira Mazando | [5 empty] | █ | █
17.2 | Response envelope - authorisation, disclosure, provenance, verification | Takawira Mazando | [5 empty] | █
17.3 | Cache keyed on scope_hash | Takawira Mazando | [6 empty] | █
17.4 | ActionAudit 'ai_report_generated' and ai.report writes | Takawira Mazando | [6 empty] | █
17.5 | Minimal report viewer page | Takawira Mazando | [6 empty] | █
17.6 | AG attestation byte-identical regression test | Takawira Mazando | [6 empty] | █
17.7 | Risk: year-end freeze compresses Phase 17 | Jerry | [6 empty] | █
18.1 | S1 role matrix - 14 roles x 2 report types | Takawira Mazando | [5 empty] | █
18.2 | S2, S3, S4, S7, S8 suites CI-gated | Takawira Mazando | [5 empty] | █ | █
18.3 | Semgrep and Bandit scans on new modules | Takawira Mazando | [6 empty] | █
18.4 | Independent RBAC / tenancy security review | SITA InfoSec | [6 empty] | █
18.5 | Load test (k6) and model-failure chaos test | Takawira Mazando | [6 empty] | █
18.6 | Diff review against main - restated non-interference claim | Jerry | [6 empty] | █
18.7 | Risk: critical finding from security review | Jerry | [6 empty] | █
BLOCK 4 - Demo, Evidence & Sign-Off
19.1 | UAT with exec, SOC and compliance personas | Jerry | [6 empty] | █
19.2 | Demonstration defects triaged and logged | Takawira Mazando | [7 empty] | █
19.3 | Evidence pack - gate results, live outputs, latency table, diff | Takawira Mazando | [6 empty] | █
19.4 | Production deployment and llm_enabled switch-on | Takawira Mazando | [8 empty] | █
19.5 | Acceptance sign-off against the POC criteria | Jerry | [8 empty] | █
19.6 | Schedule contingency buffer | Jerry | [8 empty] | █
BLOCK 2 - Scoped Data Layer & Generation Engine
14.8 | capability.py - table introspection gate and NEVER_READ denial | Takawira Mazando |  |  | █
BLOCK 4 - Demo, Evidence & Sign-Off
19.7 | Risk-bucket divergence tripwire test | Takawira Mazando | [6 empty] | █

## Decisions & Milestones
Open decisions tabled at the demonstration, and milestones
STANDING RULE: a decision not amended on 15 October is adopted as documented.
# | Decision | Owner | Default if not amended | Status
1 | Approve the ai schema in the main DB, or a separate reporting DB | Data Architect, DevOps | DEFAULT: schema 'ai' in the main database. A separate DB costs 4-6 PD of provisioning, none of it in this window. | Default ready
2 | Is estate-wide compliance disclosure acceptable, or must compliance reports wait for tenancy columns? | Compliance Analyst | DEFAULT: disclose as estate-wide. 684 rows proven unscopable live. | Default ready
3 | Does the AG require an AI narrative inside the attestation? | AG liaison | DEFAULT: keep separate. The attestation is ECDSA-signed and pure; nondeterministic text would make the signature attest to unverified text. | Default ready
4 | Is DEPARTMENT_NAMES a safe claim class for exec estate-wide? | Compliance Analyst, AG liaison | DEFAULT: ROLE_CLAIMS signed exactly as drafted. Any widening needs approval BEFORE implementation. | Default ready
5 | Audit retention for ai.report | Compliance Analyst | DEFAULT: same as audit.action_audit. Retention is not immutability - the two must not be conflated. | Default ready
6 | GPU CAPEX, sovereign cloud, or existing hardware? | Kagiso, Jerry | ANSWERED BY EVIDENCE: self-hosted Ollama on existing hardware. Zero CAPEX, zero procurement lead time. | CLOSED
7 | Team allocation for 7-14 October, including Saturday 10 October | Kagiso | DEFAULT: proceed as planned and as recorded here — Takawira 11.75 PD / 94.0 h incl. 38.0 h overtime, Peter 1.50 PD / 12.0 h, Richard advisory 0.50 PD + 4.0 h review, Victoria 6.0 h of BA support on Fri 9 Oct, Jerry 0.50 PD for the evidence pack. This asks Kagiso to accept the overtime and the single-person Saturday, not to re-allocate them. | OPEN - needed today
8 | Peter Rashaya returns for 7-14 October, taking T13, T23 and T30 | Jerry | CONFIRMED. Peter takes the three verification tasks — 1.50 PD / 12.0 h, on Fri 9, Mon 12 and Tue 13. Addendum A's 61 PD assignment to him is re-baselined, not deleted: the verifier having an author other than the prompt author is control claim 1. | CLOSED - confirmed
9 | Phase 2: authorise a date, or a re-estimate? | Kagiso, Jerry | DEFAULT: authorise a re-estimate. 29 Jan 2027 is withdrawn - it came from an estimate that assumed GPU hosting. | For 15 Oct
10 | AI tooling for the proof of concept | Richard, Kagiso | DEFAULT: private, local Ollama on the existing host, pulled on day 1 under T01. No external provider, no API key, no data leaves the environment. Sovereign cloud and any SaaS API remain available as disaster recovery only, behind the same redaction gate. Consequences if overturned: mandatory redaction, a gateway-to-provider abstraction, POPIA DPA review, and R21 retires. | Default ready
MILESTONES
ID | Milestone | Date | Proves
M0 | Model pulled, ai schema applied, Gate 1 coded | 2026-10-07 | The runtime exists and Day 1 is not blocked by a download
M1 | Gate A - RBAC and tenancy gates hold | 2026-10-08 | 403 on unknown role; fail-closed on empty scope
M2 | Gate B - scope is structurally mandatory (T13 written by Peter) | 2026-10-09 | S6 green; 2 roles produce different claim sets
M3 | Gate C - first generation from a real fact pack. CUT TRIGGER. Saturday, Takawira solo | 2026-10-10 | The agent generates from live, scoped data
M4 | Gate D - the verifier (T23, Peter) discards ungrounded output | 2026-10-12 | The control is the verifier, not the prompt
M5 | Gate E - adversarial attempts all rejected | 2026-10-13 | Tenancy containment holds under attack
M6 | FREEZE - POC frozen and evidence signed | 2026-10-14 | 17:00. No defect carried into the meeting.
M7 | CLIENT DEMONSTRATION | 2026-10-15 | The whole POC, live
M8 | Acceptance signed; Phase 2 re-estimate requested | 2026-10-16 | 29 Jan 2027 withdrawn; T01 latency table closed