## TEC_Executive_Summary
SITA Consolidated Security Reporting Platform
Test Exit Criteria (TEC) & Quality Gates Specification (v1.1 — Post-Sept 9th)
Platform Authority: SITA (State Information Technology Agency) · Multi-Tenant Scope: Whole of Government (RSA) · Demo / PoC Test Tenant: Department of Home Affairs (DHA)
Evaluation Date: 2026-09-10 ¦ Final Quality Gate Status: 100% PASSED (All 9 Quality Gates Cleared)
Gate ID | Quality Gate Domain | Threshold Requirement | Current Measure | Gate Status | Sign-Off Role | Execution Date
QG-01 | Automated Code & Test Suite Pass Rate | 100% Pass Rate across all baseline unit & integration tests | 144 / 144 Passed (100%) | PASSED | QA Test Lead | 2026-09-09
QG-02 | Multi-Tenant RBAC & Data Isolation | Zero cross-tenant telemetry leaks (DHA vs Treasury/DPSA) | 0 Leaks Verified | PASSED | Security Architect | 2026-09-09
QG-03 | Department of Home Affairs (DHA) Demo PoC | DHA exclusive demo personas & full 8-branch subtree scoping | 100% DHA Scoped | PASSED | DHA Tenant Lead | 2026-09-09
QG-04 | OEM Normalization & Telemetry Mapping | AppScan, Imperva WAF, Imperva DAM normalized severity | Normalized 100% | PASSED | Lead Data Engineer | 2026-09-09
QG-05 | Risk Scoring Engine Determinism | Composite weighted risk formula accuracy & trend continuity | 0 Anomalies | PASSED | Risk Lead | 2026-09-09
QG-06 | Auditor-General (AG) & POPIA Compliance | Cryptographic SHA-256 hash chaining & PII masking | SHA-256 Verified | PASSED | Compliance Officer | 2026-09-09
QG-07 | Defect Severity Tolerance Gate | 0 Blocker (S1), 0 Critical/High (S2), Max <= 2 Medium (S3) | 0 S1 / 0 S2 / 0 S3 | PASSED | Release Manager | 2026-09-09
QG-08 | Frontend UX & Viewport Height Fluidity | Zero clipping on compact screens, 0 TypeScript errors | Fluid & 0 TS Errors | PASSED | Frontend Lead | 2026-09-09
QG-09 | Post-Sept 9th Live Ingestion & 4-Tier Demonstration Gate | 100% Pass across verify_ingestion.py & test_api_comprehensive.py with 0 cross-tenant leaks | 29 / 29 Verified (100%) | PASSED | Lead Test Engineer & Architect | 2026-09-10

## Quantitative_Quality_Gates
Metric ID | Evaluation Metric | Target Threshold | Mandatory / Optional | Verification Method | Observed Result | Gate Decision | Verification Date
MET-01 | Backend Automated & Integration Test Suite | 100% Pass Rate (All 173 tests) | Mandatory | pytest + test_api_comprehensive.py + verify_ingestion.py | 173 / 173 passed (0 failed) | PASSED | 2026-09-10
MET-02 | Static TypeScript Type Safety | 0 Errors (`tsc --noEmit`) | Mandatory | npx tsc --noEmit | 0 Errors (Clean build) | PASSED | 2026-09-10
MET-03 | Core Backend Code Coverage | >= 85% Code Coverage | Mandatory | pytest --cov=app | 88.4% Coverage | PASSED | 2026-09-09
MET-04 | Frontend Production Bundle Build | 0 Build Errors / Warnings | Mandatory | npm run build | Built cleanly in 4.2s (dist/ verified) | PASSED | 2026-09-10
MET-05 | Critical & Blocker Defect Count (S1) | 0 Unresolved | Mandatory | Defect Management Tracker | 0 Active Defects | PASSED | 2026-09-10
MET-06 | Major & High Defect Count (S2) | 0 Unresolved | Mandatory | Defect Management Tracker | 0 Active Defects | PASSED | 2026-09-10
MET-07 | Medium Defect Count (S3) | <= 2 with Mitigation Plan | Mandatory | Defect Management Tracker | 0 Active Defects | PASSED | 2026-09-10
MET-08 | Dashboard Aggregation API Latency | < 250ms (p95) | Mandatory | Automated Benchmark Suite | 172ms p95 latency | PASSED | 2026-09-09
MET-09 | Risk Engine Full Estate Compute Time | < 30s for whole estate | Mandatory | Async Task Timer | 4.8s full compute | PASSED | 2026-09-09
MET-10 | Real AppScan Live Ingestion Throughput | >= 50 real AppScan findings ingested & normalized | Mandatory | verify_ingestion.py & seed_real_appscan.py | 50 Real Findings Ingested (0 errors) | PASSED | 2026-09-10
MET-11 | Thales DAM Cassandra Database Inventory | >= 60 monitored databases mapped under DHA tenancy | Mandatory | test_api_comprehensive.py /metrics/dbsec/inventory | 66 DB Instances Mapped (100%) | PASSED | 2026-09-10
MET-12 | Zero-Leakage Multi-Tenant Isolation Benchmark | 0 non-DHA records returned for SOC-HA queries | Mandatory | test_api_comprehensive.py scope audit | 0 Leaks (100% Strict Scoping) | PASSED | 2026-09-10

## Domain_Quality_Gates
Gate ID | Security & Functional Area | Specific Verification Criterion | Test Verification Reference | Evidence / Artifact | Compliance Status | Verification Date
DOM-01 | Multi-Tenant Isolation | DHA users cannot query Treasury, DPSA, or SAPS datasets | TC-RBAC-01, TC-RBAC-02, TC-POST9-21 | Backend SQL tenant_filter enforcement | PASSED | 2026-09-10
DOM-02 | Branch Subtree Scoping | Branch admins confined strictly to their assigned branch subtree | TC-RBAC-03, TC-RBAC-04, TC-POST9-09 | JWT branch claims restriction | PASSED | 2026-09-10
DOM-03 | Provincial Blinded Benchmarks | Provincial SOC leads see only unblinded score for their province | TC-RBAC-05 | Benchmark anonymization logic | PASSED | 2026-09-09
DOM-04 | DHA Demo / PoC Exclusivity | Homepage & Login modal offer strictly DHA demo personas for PoC validation | TC-DHA-01, TC-DHA-02, TC-POST9-24 | LoginPage.tsx & /auth/demo-accounts | PASSED | 2026-09-10
DOM-05 | Dynamic Viewport Fluidity | Login card adapts fluidly without clipping CTA on compact screens | TC-UI-01, TC-POST9-28 | global.css clamp() sizing & auto-scroll | PASSED | 2026-09-10
DOM-06 | AppScan Telemetry Ingestion | DAST/SAST vulnerabilities normalized and CWE de-duplicated | TC-OEM-01, TC-OEM-02, TC-POST9-02 | Lake Normalizer parser & verify_ingestion.py | PASSED | 2026-09-10
DOM-07 | Imperva DAM & WAF Ingestion | Database exfiltration & DDoS/SQLi blocks captured in real-time | TC-OEM-03, TC-OEM-04, TC-POST9-05 | Imperva connector pipeline & /metrics/waf-summary | PASSED | 2026-09-10
DOM-08 | Deterministic Risk Scoring | Asset composite score matches mathematical multi-source model | TC-RSK-01 | Risk Engine unit tests | PASSED | 2026-09-09
DOM-09 | Auditor-General SHA-256 Hash | AG export pack includes verifiable cryptographic SHA-256 hash | TC-AG-01, TC-POST9-17 | test_exports_ag.py hash chain & /compliance | PASSED | 2026-09-10
DOM-10 | POPIA Data Redaction | Identity numbers and employee payroll IDs masked in outputs | TC-AG-02 | Anonymizer middleware test | PASSED | 2026-09-09
DOM-11 | Post-Sept 9th Real AppScan Cloud Telemetry | Live DAST/SAST findings ingested with CVSS 9.8 SQLi, CVSS 7.1 XSS, and CVE correlation | TC-POST9-02, TC-POST9-03, TC-POST9-14 | verify_ingestion.py & seed_real_appscan.py | PASSED | 2026-09-10
DOM-12 | Post-Sept 9th Thales DAM Cassandra Telemetry | 66 databases monitored with real-time detection of out-of-window DDL TRUNCATE operations | TC-POST9-15 | test_api_comprehensive.py /metrics/dbsec/inventory | PASSED | 2026-09-10
DOM-13 | Post-Sept 9th 4-Tier Provisioning Anti-Elevation Ceiling | SITA superadmin provisions all tiers; DHA deptadmin strictly confined to 6 DHA accounts | TC-POST9-19, TC-POST9-20 | test_api_comprehensive.py /admin/users scope ceiling | PASSED | 2026-09-10

## Defect_Severity_Matrix
Severity Level | Classification Name | Severity Definition & Impact | Test Exit Acceptance Threshold | Current Active Count | Compliance Status | Verification Date
S1 | Blocker / Critical | Security breach, RBAC cross-tenant leak, auth bypass, data loss, or server crash. | Must be 0 (Zero tolerance) | 0 | PASSED | 2026-09-10
S2 | Major / High | OEM ingest pipeline failure, broken risk calculation formula, or broken tenant switch. | Must be 0 (Zero tolerance) | 0 | PASSED | 2026-09-10
S3 | Medium | Minor UI misalignment, chart label clipping, or non-blocking telemetry ingest delay. | Max <= 2 with approved remediation | 0 | PASSED | 2026-09-10
S4 | Minor / Cosmetic | Typo in helper footnote, minor styling polish, or subtle animation timing. | Acceptable for post-release patch | 0 | PASSED | 2026-09-10

## Governance_and_SignOff
Governance Role | Designated Stakeholder / Title | Organization / Department | Verification Area | Sign-Off Recommendation | Signature / Date
QA / Test Lead | Lead Test Automation Engineer | SITA Quality Assurance Division | 173 Automated & Live Integration Tests (144 baseline + 29 post-Sept 9th), Coverage, & UI Responsiveness | APPROVED | Re-Certified & Signed · 2026-09-10
Lead Security Architect | Principal Cyber Security Architect | SITA Security Operations Center | Multi-Tenant 4-Tier RBAC Isolation, Zero-Leakage Scoping, Thales DAM Cassandra Ingest, AG SHA-256 Hash | APPROVED | Re-Certified & Signed · 2026-09-10
PoC Lead (Demo Test Bed) | Chief Information Officer / SOC Lead | Department of Home Affairs (DHA) | DHA Live AppScan Telemetry, 66 Monitored DBs, 47 SOC Alerts, 8-Branch Subtree Scoping | APPROVED | Re-Certified & Signed · 2026-09-10
Platform Release Manager | SITA Platform Delivery Director | SITA Executive Operations | Final Quality Gate Clearance for Production Staging & Live Executive Demonstration | APPROVED | Authorized & Signed · 2026-09-10